## Overview
HR Change + Orchestration — Build Blueprint
Sprints, gates and progress. Mint cells are inputs; everything else is calculated.
Sprint 0 start date | 2026-10-08 | ← type your real start date (a Monday)
Sprint | Name | Phase | Weeks | Start | End | Steps | Done | % done | Gate | Gate status
S0 | Foundations | Crawl | 1 | 2026-10-08 | 2026-10-14 | 14 | 0 | 0% | G0 — Ready to build | Not started
S1 | Crawl — Path E end to end | Crawl | 2 | 2026-10-15 | 2026-10-28 | 22 | 0 | 0% | G1 — Plumbing proven | Not started
S2 | Crawl complete — Template I pilot + front door live | Crawl | 2 | 2026-10-29 | 2026-11-11 | 14 | 0 | 0% | G2 — Front door live | Not started
S3 | Walk — Approvals B/C/F + checklist progress | Walk | 2 | 2026-11-12 | 2026-11-25 | 5 | 0 | 0% | G3 — Approvals live | Not started
S4 | Walk — Daily digest, cutoff reminder, hardening | Walk | 2 | 2026-11-26 | 2026-12-09 | 5 | 0 | 0% | G4 — Operational | Not started
S5 | Walk — Downstream actions (dependency-driven) | Walk | 2 | 2026-12-10 | 2026-12-23 | 4 | 0 | 0% | G5 — per item | Not started
S6 | Run — Self-service + full audit | Run | 0 | 2026-12-24 |  | 5 | 0 | 0% | Ongoing | Not started
Total | [5 empty] | 69 | 0 | 0%
How to use this workbook:
1. Set the start date above. Sprint dates follow (S6 is ongoing).
2. Work the 'Build Steps' tab top to bottom. Set Status as you go — progress updates here.
3. Each sprint ends at a gate (Gates tab). Don't start the next sprint until every gate line is Passed.
4. Run the tests named in each sprint (Test Pack tab). Record Pass/Fail.
5. The Word document 'HR Change Blueprint' has the same steps with full explanations.
Formulas:
Start = IF([End, row above]="","",[End, row above]+1)
End = IF(OR([Start]="",[Weeks]=0),"",[Start]+[Weeks]*7-1)

## Roadmap
Roadmap — sprints and gates
Crawl → Walk → Run, as in the project plan.
Sprint | Name | Phase | Start | End | Goal | Entry criteria | Gate | Gate criteria
S0 | Foundations | Crawl | 2026-10-08 | 2026-10-14 | Reference workbook, the one list, permissions, form, views, connections. | Plan approved; this kit downloaded. | G0 — Ready to build | • D3, D5, D6 confirmed by CJ • Field list signed off with Johanna • Reference workbook uploaded and Settings filled • List built: all columns, choices, required fields, show/hide formulas, views • T21 passed (non-HR account sees only own requests)
S1 | Crawl — Path E end to end | Crawl | 2026-10-15 | 2026-10-28 | Flow 1 Intake, Flow 2 Checklist Router, Flow 4 Completion Auto-Comment. Proven on E. | G0 passed. | G1 — Plumbing proven | • T01–T06 pass • One live E submission by Johanna closed end to end • A failure alert email received from a Catch block (any test) • Flows owned by the HR/service account, not a personal one
S2 | Crawl complete — Template I pilot + front door live | Crawl | 2026-10-29 | 2026-11-11 | Flow 5 Approval Routing (HR stage for I), Flow 3 Payroll Notification, all checklists live, front door launched. | G1 passed. | G2 — Front door live | • T07–T13 pass • First real I case approved, earning entered, resolved, Payroll FYI posted • Form pinned in #lane-people-talent; manager comms sent • HR mailbox auto-reply points to the form
S3 | Walk — Approvals B/C/F + checklist progress | Walk | 2026-11-12 | 2026-11-25 | Approval chains switched on from Excel; Flow 6 Checklist Progress; UAT with Johanna. | G2 passed; approval matrix signed off. | G3 — Approvals live | • Approval matrix signed off; Approvers table filled per region • T14–T17 and T22 pass • UAT with Johanna on every path A1–I
S4 | Walk — Daily digest, cutoff reminder, hardening | Walk | 2026-11-26 | 2026-12-09 | Flow 7; exception drill; two weeks of steady operation. | G3 passed. | G4 — Operational | • T18–T20 pass • Two weeks of digests reviewed • No request handled outside the list in those two weeks • SLA baseline reviewed (All Open by SLA / Recently Resolved)
S5 | Walk — Downstream actions (dependency-driven) | Walk | 2026-12-10 | 2026-12-23 | Jira, offboarding distro, Word letters, Monday board — each only when its dependency is confirmed. | G4 passed; each item's dependency confirmed. | G5 — per item | • Dependency confirmed in writing • Built and tested on a test request • Checklist step updated to show it is automated (Auto column)
S6 | Run — Self-service + full audit | Run | 2026-12-24 |  | Manager self-service form, dashboard, in-Slack approvals, Paycor iPaaS, holiday-aware SLA. | G5 items as available. | Ongoing | • Each item ships with its own test cases and a rollback note

## Build Steps
Build Steps
Every step in order. Status is the only column you need to update (plus Done on / Notes).
ID | Sprint | Area | Step | Where | Do | Paste / settings | Check | Owner | Status | Done on | Notes
S0-01 | S0 | Decisions | Confirm the open design decisions | Decisions tab | • Review D3 (front door), D5 (Template I: Payroll verifier, not gate), D6 (Manager person field). • Mark each Confirmed / Changed in the Decisions tab. |  | D3, D5, D6 no longer say 'Confirm'. | CJ | Not started
S0-02 | S0 | Excel | Store the reference workbook | People Ops SharePoint site → Documents | • Create a folder 'HR Change' and upload HR Change Reference.xlsx. • Folder → Manage access: HR owners can edit; everyone else no access. • Read the About sheet: never rename a table (tblSettings, tblChangeTypes, tblChecklist, tblApprovers) or a column header. |  | The file opens in Excel for the web and Table Design shows the four table names. | CJ | Not started
S0-03 | S0 | Excel | Fill in Settings | HR Change Reference.xlsx → Settings | • Set TimeZone, CutoffDay1, CutoffDay2 (your real payroll cutoffs), ReminderBusinessDays and AdminEmail. • Leave IntakeFormUrl for S0-14. |  | No '<' placeholders left except IntakeFormUrl. | Johanna | Not started
S0-04 | S0 | Excel | Review Change Types | HR Change Reference.xlsx → Change Types | • Check SLA days and the Due Date Rule for every type (Business days / Effective date / None). • Set DefaultAssigneeEmail where a type always goes to the same person (G → CJ is pre-filled). • Leave ApprovalChain blank for B, C, F until Sprint 3 (decision D13). I = 'HR' (pilot). • Decide Sensitive for H (A2 and G are Yes). |  | Every row has Code, ChangeType, DueDateRule; Yes/No columns contain only Yes or No. | Johanna | Not started
S0-05 | S0 | Excel | Review the checklists against the SOP | HR Change Reference.xlsx → Checklists | • Walk A1–I with Johanna. Edit Task / Details / Owner as needed. Keep Step as two digits (01, 02 …). • Auto: 'approval' = ticked by the approvals flow; 'resolution' = ticked when the case is resolved. AfterApproval = Yes shows 🔒. |  | Johanna signs off each change type's steps. | Johanna | Not started
S0-06 | S0 | Excel | Draft the Approvers table | HR Change Reference.xlsx → Approvers | • One row per Role (Regional, HR, Payroll) and Region. Region '*' = default for any region. • Region values must match the list's Region choices exactly. |  | An HR row with Region '*' and Active = Yes exists (needed for the I pilot). | CJ | Not started
S0-07 | S0 | SharePoint | Create the list from CSV | Site → + New → List → From CSV → HR-Change-Requests.csv | • Keep the headers exactly (no spaces = internal names the flows use). • In the preview, set each column type per the List Fields tab. • Name the list 'HR Change Requests' → Create. Delete the SAMPLE row. |  | List settings → Columns shows internal names without spaces (hover a column: Field=EmployeeName). | Johanna | Not started
S0-08 | S0 | SharePoint | Finish the choice columns | List → column header → Column settings → Edit | • For every Choice column, paste the full choice list from the List Fields tab (one per line). • Defaults: Status = 0-New, ApprovalStatus = Not required. |  | New form shows all 11 Change Type values. | Johanna | Not started
S0-09 | S0 | SharePoint | Add the three Person columns | List → + Add column → Person | • Manager (required), Assignee, RequestedBy — type the name without spaces first; rename the display name afterwards if you like. |  | All three appear in the New form / list settings. | Johanna | Not started
S0-10 | S0 | SharePoint | Required fields + permissions | List settings | • Required: EmployeeName, EmployeeId, Manager, ChangeType, EffectiveDate. • Advanced settings → Read access: 'Read items that were created by the user'; Create and Edit access: 'Create items and edit items that were created by the user'. • HR team: Full Control (or Edit + Override List Behaviors) so they see everything. |  | Test T21 with a non-HR colleague. | CJ | Not started
S0-11 | S0 | SharePoint | Show/hide formulas on the form | List → + New → Edit form (pencil) → Edit columns → column ⋯ → Edit conditional formula | • Paste the 'Show formula' from the List Fields tab for every Conditional and Case column. • Drag the universal fields to the top in Slack-form order: Employee Name, Employee ID, Manager, Change Type, Effective Date, Region, Additional Notes. |  | Choosing 'C — Comp Change' shows New Rate + Effective Pay Period only; case fields are hidden on New. | Johanna | Not started
S0-12 | S0 | SharePoint | Create the workbench views | List → All Items → Create new view | • Create the 8 views on the Views tab (filters, sort/group, columns). |  | 'Needs Attention Today' and 'Exceptions' exist. | Johanna | Not started
S0-13 | S0 | Power Automate | Create the connections | make.powerautomate.com → Data → Connections | • Slack: sign in as the People Ops service account (D9). • SharePoint, Office 365 Outlook, Excel Online (Business), Approvals: the HR flow-owner account (Full Control on the site). |  | Five connections show 'Connected'. | CJ | Not started
S0-14 | S0 | Excel | Record the front door link | List → + New | • Copy the browser address of the New form into Settings → IntakeFormUrl. |  | The link opens the New form for a non-HR user. | Johanna | Not started
S1-01 | S1 | Flow 1 | Create 'HR Change - 1 Intake Notification' | My flows → + New flow → Automated cloud flow | • Trigger: SharePoint — When an item is created · Site: People Ops · List: HR Change Requests. • Add Control → Scope, rename it 'Try'. Build every following action INSIDE Try. |  | Saved with trigger + empty Try. | Johanna | Not started
S1-02 | S1 | Flow 1 | Add the standard opening block | Inside Try | • Add the six actions of the Standard opening block (Appendix A), renamed exactly. | Settings row (Excel Online (Business) → List rows present in a table): Location: your People Ops site · Document Library: Documents · File: HR Change/HR Change Reference.xlsx · Table: tblSettings Settings (Compose): first(outputs('Settings_row')?['body/value']) Code (Compose): first(split(triggerBody()?['ChangeType']?['Value'], ' ')) Change type row (Excel → List rows present in a table) — Table: tblChangeTypes · Filter Query:: Code eq '@{outputs('Code')}' Config (Compose): first(outputs('Change_type_row')?['body/value']) Request ID (Compose): concat(outputs('Settings')?['RequestPrefix'], formatNumber(triggerBody()?['ID'], '000000')) | Run once (Test → Manually, then create an E request): Config shows the E row. | Johanna | Not started
S1-03 | S1 | Flow 1 | SLA due date | Inside Try, after Request ID | • Four Compose actions, renamed as shown. | Submitted Local: convertFromUtc(triggerBody()?['Created'], outputs('Settings')?['TimeZone']) SLA Start (weekend submissions start Monday): addDays(startOfDay(outputs('Submitted_Local')), if(equals(dayOfWeek(outputs('Submitted_Local')), 6), 2, if(equals(dayOfWeek(outputs('Submitted_Local')), 0), 1, 0))) SLA Days: if(empty(outputs('Config')?['SLABusinessDays']), 0, int(outputs('Config')?['SLABusinessDays'])) SLA Due Date: if(equals(outputs('Config')?['DueDateRule'], 'Effective date'), formatDateTime(coalesce(triggerBody()?['LastDay'], triggerBody()?['EffectiveDate']), 'yyyy-MM-dd'), if(equals(outputs('SLA_Days'), 0), null, formatDateTime(addDays(outputs('SLA_Start'), add(add(mul(div(outputs('SLA_Days'), 5), 7), mod(outputs('SLA_Days'), 5)), if(greater(add(dayOfWeek(outputs('SLA_Start')), mod(outputs('SLA_Days'), 5)), 5), 2, 0))), 'yyyy-MM-dd'))) | E submitted Monday → SLA Due Date = Tuesday. | Johanna | Not started
S1-04 | S1 | Flow 1 | Pay period + cutoff flag (used by type I) | Inside Try | • Four Compose actions. Harmless for other change types. | Pay Period Date: coalesce(triggerBody()?['StartDate'], triggerBody()?['EffectiveDate']) Pay Period: concat(formatDateTime(outputs('Pay_Period_Date'), 'yyyy-MM'), if(lessOrEquals(dayOfMonth(outputs('Pay_Period_Date')), 15), ' (1-15)', ' (16-EOM)')) Cutoff Date: addDays(startOfMonth(outputs('Pay_Period_Date')), sub(int(if(lessOrEquals(dayOfMonth(outputs('Pay_Period_Date')), 15), outputs('Settings')?['CutoffDay1'], outputs('Settings')?['CutoffDay2'])), 1)) After Cutoff: and(equals(outputs('Code'), 'I'), greater(ticks(outputs('Submitted_Local')), ticks(addDays(outputs('Cutoff_Date'), 1)))) | For E: After Cutoff = false. | Johanna | Not started
S1-05 | S1 | Flow 1 | Write ID, title and SLA back to the item | Inside Try → SharePoint → Update item | • List: HR Change Requests · Id: ID (trigger). • Required columns the action asks for: pick the SAME field from the trigger (it writes back what is already there). • Do not set Status or ApprovalStatus here — column defaults cover intake and Flow 5 owns approvals. | Title (fx): concat(triggerBody()?['ChangeType']?['Value'], ' — ', triggerBody()?['EmployeeName']) RequestId (fx): outputs('Request_ID') RequestedBy Claims (fx): triggerBody()?['Author']?['Email'] SLADueDate (fx): outputs('SLA_Due_Date') NextActionDue (fx): outputs('SLA_Due_Date') PayPeriod (fx): if(equals(outputs('Code'), 'I'), outputs('Pay_Period'), '') AfterCutoff (fx): outputs('After_Cutoff') | Item shows Request = 'E — Personal Data Change — <name>' and Request ID HRC-00000N. | Johanna | Not started
S1-06 | S1 | Flow 1 | Default assignee (from Change Types) | Inside Try → Control → Condition 'Default assignee?' | • Left (fx) and(empty(triggerBody()?['Assignee']), not(empty(coalesce(outputs('Config')?['DefaultAssigneeEmail'], '')))) · is equal to · (fx) true • True → Update item 'Set default assignee' (required columns from trigger). | Assignee Claims (fx): outputs('Config')?['DefaultAssigneeEmail'] | A G request gets CJ as Assignee. | Johanna | Not started
S1-07 | S1 | Flow 1 | Intake comment on the thread | Inside Try — Comment pattern (Appendix B) | • Add 'Display Name' Compose first (used by Slack too). Then the Comment pattern named 'Intake'. | Display Name (Compose): if(equals(outputs('Config')?['Sensitive'], 'Yes'), '(confidential — see list)', triggerBody()?['EmployeeName']) Intake text (Compose): 📥 @{outputs('Request_ID')} received from @{triggerBody()?['Author']?['DisplayName']}. SLA target: @{coalesce(outputs('SLA_Due_Date'), outputs('Config')?['SLATarget'])}.@{if(outputs('After_Cutoff'), ' ⚠️ Submitted after the payroll cutoff for this pay period.', '')} Post intake — Body (fx): setProperty(json('{}'), 'text', take(outputs('Intake_text'), 1900)) | Comment appears in the item's Comments pane. | Johanna | Not started
S1-08 | S1 | Flow 1 | Ping the People Ops room | Inside Try → Slack → Post message (V2) | • Channel: People Ops room. Message text below. | Message text: :inbox_tray: *New HR change request <@{triggerBody()?['{Link}']}¦@{outputs('Request_ID')}>* @{triggerBody()?['ChangeType']?['Value']} — @{outputs('Display_Name')} Effective @{formatDateTime(triggerBody()?['EffectiveDate'], 'MMM d, yyyy')} • SLA target @{coalesce(outputs('SLA_Due_Date'), outputs('Config')?['SLATarget'])}@{if(outputs('After_Cutoff'), ' • :warning: after payroll cutoff', '')} | Message posts; for A2/G the name shows '(confidential — see list)'. | Johanna | Not started
S1-09 | S1 | Flow 1 | Confirmation to the submitter | Inside Try → Office 365 Outlook → Send an email (V2) | • Wording sets expectations without promising a date. | To (fx): triggerBody()?['Author']?['Email'] Subject: We've got your request: @{outputs('Request_ID')} Body: Hi @{triggerBody()?['Author']?['DisplayName']}, Thanks for using the HR front door. Your request @{outputs('Request_ID')} (@{triggerBody()?['ChangeType']?['Value']}) is in the People Ops queue. Target completion: @{coalesce(outputs('SLA_Due_Date'), outputs('Config')?['SLATarget'])}. This is an automatic confirmation — a team member will pick it up and keep you posted. Follow along here: @{triggerBody()?['{Link}']} People Ops | Email arrives. | Johanna | Not started
S1-10 | S1 | Flow 1 | Add the Catch block | Below Try (not inside) | • Add the Try / Catch pattern (Appendix C). | Catch (Control → Scope) → ⋯ → Configure run after: Try: ☑ has failed ☑ has timed out (☐ is successful) Failure alert (Office 365 Outlook → Send an email (V2)) — To: your admin email (type it — don't depend on Settings here) Subject: [HR Change] @{workflow()?['tags']?['flowDisplayName']} failed Body: Open the failed run: @{concat('https://make.powerautomate.com/environments/', workflow()?['tags']?['environmentName'], '/flows/', workflow()?['name'], '/runs/', workflow()?['run']?['name'])} Flag the item (SharePoint → Update item, item-triggered flows only) — AutomationNote (fx): concat('⚠️ ', workflow()?['tags']?['flowDisplayName'], ' failed ', formatDateTime(utcNow(), 'yyyy-MM-dd HH:mm'), ' UTC — see admin email') | Configure run after shows only 'has failed' and 'has timed out'. | Johanna | Not started
S1-11 | S1 | Test | Test Flow 1 | Test → Manually → create an E request | • Run T01 and T02 from the Test Pack. |  | T01, T02 = Pass. | Johanna | Not started
S1-12 | S1 | Flow 2 | Create 'HR Change - 2 Checklist Router' | Automated cloud flow | • Trigger: SharePoint — When an item is created · List: HR Change Requests. (Separate from Flow 1 on purpose: one failing can't stop the other.) • Add Scope 'Try' and the Standard opening block inside it. | Settings row (Excel Online (Business) → List rows present in a table): Location: your People Ops site · Document Library: Documents · File: HR Change/HR Change Reference.xlsx · Table: tblSettings Settings (Compose): first(outputs('Settings_row')?['body/value']) Code (Compose): first(split(triggerBody()?['ChangeType']?['Value'], ' ')) Change type row (Excel → List rows present in a table) — Table: tblChangeTypes · Filter Query:: Code eq '@{outputs('Code')}' Config (Compose): first(outputs('Change_type_row')?['body/value']) Request ID (Compose): concat(outputs('Settings')?['RequestPrefix'], formatNumber(triggerBody()?['ID'], '000000')) | Saved. | Johanna | Not started
S1-13 | S1 | Flow 2 | Read this change type's checklist | Inside Try | • Excel → List rows present in a table 'Checklist rows': Table tblChecklist, Filter Query and Order By below. • Data Operation → Filter array 'Active steps', advanced mode. | Checklist rows — Filter Query: Code eq '@{outputs('Code')}' Checklist rows — Order By: Step Active steps — From (fx): outputs('Checklist_rows')?['body/value'] Active steps — advanced mode: @equals(item()?['Active'], 'Yes') | For E: Active steps returns 5 rows. | Johanna | Not started
S1-14 | S1 | Flow 2 | Build the checklist and post it | Inside Try → Condition 'Has checklist' | • Left (fx) length(body('Active_steps')) · is greater than · 0. • True branch: two Selects (Map in text mode — the T icon), one Compose, Update item, Comment pattern 'Checklist'. | Checklist lines — Select From (fx): body('Active_steps') Checklist lines — Map (fx): concat('[ ] ', item()?['Step'], '. ', item()?['Task'], if(equals(item()?['AfterApproval'], 'Yes'), ' 🔒', ''), if(equals(item()?['DueOnLastDay'], 'Yes'), concat(' 📅 ', formatDateTime(coalesce(triggerBody()?['LastDay'], triggerBody()?['EffectiveDate']), 'MMM d')), ''), if(empty(item()?['Auto']), '', concat(' ⚙ ', item()?['Auto']))) Comment lines — Select From (fx): body('Active_steps') Comment lines — Map (fx): concat('☐ ', item()?['Step'], '. ', item()?['Task'], if(empty(item()?['Details']), '', concat(' — ', item()?['Details']))) Checklist text (Compose, fx): join(body('Checklist_lines'), decodeUriComponent('%0A')) Save checklist (Update item) — Checklist (fx): outputs('Checklist_text') Save checklist — ChecklistProgress: 0 Save checklist — NextAction (fx): concat(first(body('Active_steps'))?['Step'], '. ', first(body('Active_steps'))?['Task']) Checklist text for the thread — 'Checklist comment text' (Compose): 📋 @{outputs('Code')} checklist — @{length(body('Active_steps'))} steps. Tick them in the Checklist field by changing [ ] to [x]. @{join(body('Comment_lines'), decodeUriComponent('%0A'))} Post checklist comment — Body (fx): setProperty(json('{}'), 'text', take(outputs('Checklist_comment_text'), 1900)) | E item: Checklist field has 5 '[ ]' lines; Next Action = '01. Confirm field(s) changing and new value'; checklist comment posted. | Johanna | Not started
S1-15 | S1 | Flow 2 | Catch-all for 'Other' | Condition 'Has checklist' → False branch | • Comment pattern 'No template' + Slack post to the People Ops room. | No template text (Compose): ⚠️ No checklist for change type @{outputs('Code')} — needs manual scoping. Set an Assignee and write the steps into the Checklist field. Slack message: :warning: <@{triggerBody()?['{Link}']}¦@{outputs('Request_ID')}> (@{triggerBody()?['ChangeType']?['Value']}) has no checklist — needs manual scoping. | T04 passes. | Johanna | Not started
S1-16 | S1 | Flow 2 | Catch block + test | Below Try | • Add the Catch pattern. Run T03 and T04. | Catch (Control → Scope) → ⋯ → Configure run after: Try: ☑ has failed ☑ has timed out (☐ is successful) Failure alert (Office 365 Outlook → Send an email (V2)) — To: your admin email (type it — don't depend on Settings here) Subject: [HR Change] @{workflow()?['tags']?['flowDisplayName']} failed Body: Open the failed run: @{concat('https://make.powerautomate.com/environments/', workflow()?['tags']?['environmentName'], '/flows/', workflow()?['name'], '/runs/', workflow()?['run']?['name'])} Flag the item (SharePoint → Update item, item-triggered flows only) — AutomationNote (fx): concat('⚠️ ', workflow()?['tags']?['flowDisplayName'], ' failed ', formatDateTime(utcNow(), 'yyyy-MM-dd HH:mm'), ' UTC — see admin email') | T03, T04 = Pass. | Johanna | Not started
S1-17 | S1 | Flow 4 | Create 'HR Change - 4 Completion Auto-Comment' | Automated cloud flow | • Trigger: SharePoint — When an item is created or modified · List: HR Change Requests. • Trigger ⋯ → Settings → Trigger conditions (two lines). They make it fire once per resolution — the flow stamps Completion Date, so its own update can't re-fire it. • Add Scope 'Try' + opening block (you can skip 'Request ID'). | Trigger condition 1: @equals(triggerBody()?['Status']?['Value'], '3-Resolved') Trigger condition 2: @empty(triggerBody()?['CompletionDate']) Settings row (Excel Online (Business) → List rows present in a table): Location: your People Ops site · Document Library: Documents · File: HR Change/HR Change Reference.xlsx · Table: tblSettings Settings (Compose): first(outputs('Settings_row')?['body/value']) Code (Compose): first(split(triggerBody()?['ChangeType']?['Value'], ' ')) Change type row (Excel → List rows present in a table) — Table: tblChangeTypes · Filter Query:: Code eq '@{outputs('Code')}' Config (Compose): first(outputs('Change_type_row')?['body/value']) | Saved. | Johanna | Not started
S1-18 | S1 | Flow 4 | Work out outcome, resolver and the ticked checklist | Inside Try | • Compose × 4, Select × 1, Filter array × 1. | Outcome: coalesce(triggerBody()?['Outcome']?['Value'], 'Completed') Resolver: coalesce(triggerBody()?['Assignee']?['DisplayName'], triggerBody()?['Editor']?['DisplayName']) Today: convertFromUtc(utcNow(), outputs('Settings')?['TimeZone']) Checklist before: split(replace(coalesce(triggerBody()?['Checklist'], ''), decodeUriComponent('%0D'), ''), decodeUriComponent('%0A')) Checklist after — Select From (fx) / Map (fx): outputs('Checklist_before') · if(and(startsWith(item(), '[ ]'), or(contains(item(), '⚙ resolution'), not(equals(outputs('Outcome'), 'Completed')))), concat(if(equals(outputs('Outcome'), 'Completed'), '[x]', '[–]'), substring(item(), 3)), item()) Still open — Filter array From (fx) / advanced: body('Checklist_after') · @startsWith(item(), '[ ]') | On an E resolve: Checklist after shows steps 03–05 as [x]. | Johanna | Not started
S1-19 | S1 | Flow 4 | Stamp completion and post ✅ | Inside Try | • Update item 'Stamp completion' (required columns from trigger), then Comment pattern 'Resolved'. | CompletionDate (fx): formatDateTime(outputs('Today'), 'yyyy-MM-dd') Outcome Value (fx): outputs('Outcome') Checklist (fx): if(empty(triggerBody()?['Checklist']), '', join(body('Checklist_after'), decodeUriComponent('%0A'))) NextAction (fx): '' Resolved text (Compose): ✅ Resolved on @{formatDateTime(outputs('Today'), 'MMM d, yyyy')} by @{outputs('Resolver')}@{if(equals(outputs('Outcome'), 'Completed'), '', concat(' (Outcome: ', outputs('Outcome'), ')'))}@{if(greater(length(body('Still_open')), 0), concat(' — note: ', string(length(body('Still_open'))), ' checklist step(s) were still open'), '')} | Comment reads '✅ Resolved on <date> by <assignee>'. | Johanna | Not started
S1-20 | S1 | Flow 4 | Close-the-loop + People Ops summary | Inside Try | • Condition 'Close the loop?': Left (fx) or(equals(outputs('Config')?['CloseLoopEmail'], 'Yes'), not(equals(outputs('Outcome'), 'Completed'))) · is equal to · (fx) true → Send an email (V2). • Condition 'Summary to People Ops?': Left (fx) equals(outputs('Config')?['PostSummaryToPeopleOps'], 'Yes') · is equal to · (fx) true → Slack Post message (V2) to the People Ops room. | Email To (fx): coalesce(triggerBody()?['RequestedBy']?['Email'], triggerBody()?['Author']?['Email']) Email Subject: Update on your HR request @{triggerBody()?['RequestId']} Email Body: Hi @{coalesce(triggerBody()?['RequestedBy']?['DisplayName'], triggerBody()?['Author']?['DisplayName'])}, @{if(equals(outputs('Outcome'), 'Completed'), concat('Good news — your request ', triggerBody()?['RequestId'], ' (', triggerBody()?['ChangeType']?['Value'], ') is complete.'), concat('Your request ', triggerBody()?['RequestId'], ' (', triggerBody()?['ChangeType']?['Value'], ') was closed as ', outputs('Outcome'), '.'))} @{if(empty(triggerBody()?['ApprovalHistory']), '', concat('Approval notes: ', triggerBody()?['ApprovalHistory']))} Questions? Just reply in #lane-people-talent or open the request: @{triggerBody()?['{Link}']} People Ops Slack summary: :white_check_mark: *<@{triggerBody()?['{Link}']}¦@{triggerBody()?['RequestId']}>* @{outputs('Code')} resolved by @{outputs('Resolver')} (@{outputs('Outcome')}).@{if(greater(length(body('Still_open')), 0), concat(' :warning: ', string(length(body('Still_open'))), ' step(s) still open.'), '')} | T05 passes. | Johanna | Not started
S1-21 | S1 | Flow 4 | Catch block + test | Below Try | • Catch pattern. Run T05. | Catch (Control → Scope) → ⋯ → Configure run after: Try: ☑ has failed ☑ has timed out (☐ is successful) Failure alert (Office 365 Outlook → Send an email (V2)) — To: your admin email (type it — don't depend on Settings here) Subject: [HR Change] @{workflow()?['tags']?['flowDisplayName']} failed Body: Open the failed run: @{concat('https://make.powerautomate.com/environments/', workflow()?['tags']?['environmentName'], '/flows/', workflow()?['name'], '/runs/', workflow()?['run']?['name'])} Flag the item (SharePoint → Update item, item-triggered flows only) — AutomationNote (fx): concat('⚠️ ', workflow()?['tags']?['flowDisplayName'], ' failed ', formatDateTime(utcNow(), 'yyyy-MM-dd HH:mm'), ' UTC — see admin email') | T05 = Pass. | Johanna | Not started
S1-22 | S1 | Test | Live E submission | Real request | • Johanna submits one real Personal Data Change, works the checklist and resolves it (T06). |  | Gate G1 checklist complete. | Johanna | Not started
S2-01 | S2 | Flow 5 | Create 'HR Change - 5 Approval Routing' | Automated cloud flow | • Trigger: When an item is created · List: HR Change Requests. • BEFORE the Try scope (variables can't live inside a scope): Initialize variable 'Outcome' (String) = Approved; Initialize variable 'History' (String) = empty. • Then Scope 'Try' + opening block. | Settings row (Excel Online (Business) → List rows present in a table): Location: your People Ops site · Document Library: Documents · File: HR Change/HR Change Reference.xlsx · Table: tblSettings Settings (Compose): first(outputs('Settings_row')?['body/value']) Code (Compose): first(split(triggerBody()?['ChangeType']?['Value'], ' ')) Change type row (Excel → List rows present in a table) — Table: tblChangeTypes · Filter Query:: Code eq '@{outputs('Code')}' Config (Compose): first(outputs('Change_type_row')?['body/value']) Request ID (Compose): concat(outputs('Settings')?['RequestPrefix'], formatNumber(triggerBody()?['ID'], '000000')) | Saved. | Johanna | Not started
S2-02 | S2 | Flow 5 | Read the approval chain | Inside Try | • Filter array 'Stages'; Condition 'Needs approval' (Left fx length(body('Stages')) · is greater than · 0). Everything below goes in its True branch. | Stages — From (fx): split(replace(coalesce(outputs('Config')?['ApprovalChain'], ''), ' ', ''), '>') Stages — advanced: @not(empty(item())) | For I: Stages = ["HR"]. For E: empty → nothing happens. | Johanna | Not started
S2-03 | S2 | Flow 5 | Mark the request as waiting | True branch | • Excel List rows 'Approvers rows' (Table tblApprovers, no filter). • Update item 'Mark pending' (required columns from trigger). | ApprovalStatus Value: Pending Status Value: 2-Waiting WaitingOn Value: Approver | Item shows 2-Waiting / Pending / Approver. | Johanna | Not started
S2-04 | S2 | Flow 5 | Loop the stages one at a time | True branch → Apply to each 'Each stage' | • Select an output (fx): body('Stages'). • ⚠️ Each stage ⋯ → Settings → Concurrency control ON, Degree of parallelism = 1. • Inside the loop: Condition 'Still approved' — Left (fx) variables('Outcome') · is equal to · Approved. Steps S2-05 to S2-07 go in its True branch. |  | Concurrency shows 1. | Johanna | Not started
S2-05 | S2 | Flow 5 | Find the approver for this stage | Still approved → True | • Filter array 'This region' and 'Any region' (From fx outputs('Approvers_rows')?['body/value']), then Compose 'Approver'. | This region — advanced: @and(equals(item()?['Role'], items('Each_stage')), equals(item()?['Active'], 'Yes'), equals(toLower(trim(item()?['Region'])), toLower(trim(coalesce(triggerBody()?['Region']?['Value'], ''))))) Any region — advanced: @and(equals(item()?['Role'], items('Each_stage')), equals(item()?['Active'], 'Yes'), equals(trim(item()?['Region']), '*')) Approver (Compose): if(equals(items('Each_stage'), 'Manager'), coalesce(triggerBody()?['Manager']?['Email'], ''), coalesce(first(body('This_region'))?['ApproverEmail'], first(body('Any_region'))?['ApproverEmail'], '')) | For I: Approver = the HR row's email. | Johanna | Not started
S2-06 | S2 | Flow 5 | Ask, record, and stop on reject | Condition 'Approver found' (Left fx empty(outputs('Approver')) · is equal to · fx false) → True | • Update item 'Show approver'; Approvals → Start and wait for an approval 'Approval' (Approve/Reject – First to respond); Append to string variable 'History'; Comment pattern 'Decision'; Condition 'Rejected?' (Left fx outputs('Approval')?['body/outcome'] · is equal to · Reject) → True: Set variable Outcome = Rejected. | Show approver — CurrentApprover: @{items('Each_stage')}: @{outputs('Approver')} Approval — Title: @{items('Each_stage')} approval: @{triggerBody()?['ChangeType']?['Value']} — @{triggerBody()?['EmployeeName']} [@{outputs('Request_ID')}] Approval — Assigned to (fx): outputs('Approver') Approval — Details: **Employee:** @{triggerBody()?['EmployeeName']} (@{triggerBody()?['EmployeeId']}) **Change type:** @{triggerBody()?['ChangeType']?['Value']} **Effective date:** @{formatDateTime(triggerBody()?['EffectiveDate'], 'MMM d, yyyy')} **Job change:** @{triggerBody()?['NewTitle']} @{triggerBody()?['NewDepartment']} @{triggerBody()?['NewLocation']} @{triggerBody()?['EmploymentStatus']?['Value']} **Comp:** @{triggerBody()?['NewRate']} @{triggerBody()?['EffectivePayPeriod']} **Extra shift:** @{triggerBody()?['DatesWorked']} @{triggerBody()?['ShiftType']?['Value']} @{triggerBody()?['RateType']?['Value']} @{triggerBody()?['RateAmount']} × @{triggerBody()?['HoursOrDays']} — pay period @{triggerBody()?['PayPeriod']} **Notes:** @{triggerBody()?['Notes']} Approval — Item link (fx) / description: triggerBody()?['{Link}'] · Open @{outputs('Request_ID')} History — value (end with Enter): @{items('Each_stage')}: @{if(equals(outputs('Approval')?['body/outcome'], 'Approve'), 'Approved', 'Rejected')} by @{first(outputs('Approval')?['body/responses'])?['responder']?['displayName']} on @{formatDateTime(convertFromUtc(utcNow(), outputs('Settings')?['TimeZone']), 'MMM d, yyyy')}@{if(empty(first(outputs('Approval')?['body/responses'])?['comments']), '', concat(' — ', first(outputs('Approval')?['body/responses'])?['comments']))} Decision text (Compose): @{if(equals(outputs('Approval')?['body/outcome'], 'Approve'), '👍', '👎')} @{items('Each_stage')} @{if(equals(outputs('Approval')?['body/outcome'], 'Approve'), 'approved', 'rejected')} by @{first(outputs('Approval')?['body/responses'])?['responder']?['displayName']}@{if(empty(first(outputs('Approval')?['body/responses'])?['comments']), '', concat(': ', first(outputs('Approval')?['body/responses'])?['comments']))} | Approval email arrives; decision comment appears. | Johanna | Not started
S2-07 | S2 | Flow 5 | No approver found | Condition 'Approver found' → False | • Set variable Outcome = NoApprover; Slack post to the People Ops room. | Slack message: :rotating_light: <@{triggerBody()?['{Link}']}¦@{outputs('Request_ID')}> needs a *@{items('Each_stage')}* approver but none was found (Manager empty, or no active Approvers row for this role/region). | T16 passes (Sprint 3). | Johanna | Not started
S2-08 | S2 | Flow 5 | Save the result after the loop | Needs approval → True, AFTER the loop | • SharePoint Get item 'Request now' (Id = trigger ID). Select 'Approval ticks'. Update item 'Save approval result' (required columns from Request now). Comment pattern 'Result'. | Approval ticks — From (fx): split(replace(coalesce(outputs('Request_now')?['body/Checklist'], ''), decodeUriComponent('%0D'), ''), decodeUriComponent('%0A')) Approval ticks — Map (fx): if(and(startsWith(item(), '[ ]'), contains(item(), '⚙ approval')), concat('[x]', substring(item(), 3)), item()) ApprovalStatus Value (fx): if(equals(variables('Outcome'), 'Approved'), 'Approved', if(equals(variables('Outcome'), 'Rejected'), 'Rejected', 'Needs approver')) Status Value (fx): if(equals(variables('Outcome'), 'Rejected'), '3-Resolved', if(equals(variables('Outcome'), 'NoApprover'), '2-Waiting', if(empty(outputs('Request_now')?['body/Assignee']), '0-New', '1-Assigned'))) Outcome Value (fx): if(equals(variables('Outcome'), 'Rejected'), 'Rejected', outputs('Request_now')?['body/Outcome']?['Value']) WaitingOn Value (fx): if(equals(variables('Outcome'), 'NoApprover'), 'Approver', null) CurrentApprover (fx) / ApprovalHistory (fx): '' · variables('History') Checklist (fx): if(or(equals(variables('Outcome'), 'NoApprover'), empty(outputs('Request_now')?['body/Checklist'])), outputs('Request_now')?['body/Checklist'], join(body('Approval_ticks'), decodeUriComponent('%0A'))) Result text (Compose): @{if(equals(variables('Outcome'), 'Approved'), concat('🔓 Approved (', join(body('Stages'), ' → '), '). 🔒 steps can start now.'), if(equals(variables('Outcome'), 'Rejected'), '⛔ Rejected — case closed as Rejected; the requester will be told.', '⚠️ Approval stopped: no approver found. Fix the Manager field or the Approvers table, then approve offline and log it here.'))} | T07: after approving, ApprovalStatus = Approved and step 01 is [x]. | Johanna | Not started
S2-09 | S2 | Flow 5 | Catch block | Below Try | • Catch pattern. | Catch (Control → Scope) → ⋯ → Configure run after: Try: ☑ has failed ☑ has timed out (☐ is successful) Failure alert (Office 365 Outlook → Send an email (V2)) — To: your admin email (type it — don't depend on Settings here) Subject: [HR Change] @{workflow()?['tags']?['flowDisplayName']} failed Body: Open the failed run: @{concat('https://make.powerautomate.com/environments/', workflow()?['tags']?['environmentName'], '/flows/', workflow()?['name'], '/runs/', workflow()?['run']?['name'])} Flag the item (SharePoint → Update item, item-triggered flows only) — AutomationNote (fx): concat('⚠️ ', workflow()?['tags']?['flowDisplayName'], ' failed ', formatDateTime(utcNow(), 'yyyy-MM-dd HH:mm'), ' UTC — see admin email') | Saved. | Johanna | Not started
S2-10 | S2 | Flow 3 | Create 'HR Change - 3 Payroll Notification' (Template I only) | Automated cloud flow | • Trigger: When an item is created or modified · List: HR Change Requests. Trigger conditions (4 lines) below. • Try: Settings row + Settings; Slack post to the Payroll room; Update item 'Mark payroll notified'; Comment pattern 'Payroll'. Then Catch. • One-way FYI: it never waits for Payroll (decision D5). | Trigger condition 1: @equals(triggerBody()?['Status']?['Value'], '3-Resolved') Trigger condition 2: @startsWith(triggerBody()?['ChangeType']?['Value'], 'I ') Trigger condition 3: @empty(triggerBody()?['PayrollNotifiedOn']) Trigger condition 4: @not(equals(triggerBody()?['Outcome']?['Value'], 'Rejected')) Slack message (Payroll room): :moneybag: *Extra shift earning submitted in Paycor* — <@{triggerBody()?['{Link}']}¦@{triggerBody()?['RequestId']}> Employee: @{triggerBody()?['EmployeeName']} (@{triggerBody()?['EmployeeId']}) Dates worked: @{coalesce(triggerBody()?['DatesWorked'], '-')} • Shift: @{coalesce(triggerBody()?['ShiftType']?['Value'], '-')} Rate: @{coalesce(triggerBody()?['RateType']?['Value'], '-')} @{coalesce(string(triggerBody()?['RateAmount']), '')} • Hours/days: @{coalesce(string(triggerBody()?['HoursOrDays']), '-')} Pay period: @{coalesce(triggerBody()?['PayPeriod'], '-')}@{if(equals(triggerBody()?['AfterCutoff'], true), ' :warning: submitted after cutoff', '')} _FYI — please verify the earning in Paycor. No response needed._ Mark payroll notified — PayrollNotifiedOn (fx): formatDateTime(convertFromUtc(utcNow(), outputs('Settings')?['TimeZone']), 'yyyy-MM-dd') Payroll text (Compose): 💰 Payroll notified to verify the Paycor earning (FYI — not a gate). | T10 passes. | Johanna | Not started
S2-11 | S2 | Test | Template I pilot tests | Test Pack | • Run T07, T08, T09, T10. |  | All pass. | Johanna | Not started
S2-12 | S2 | Test | LOA and offboarding paths | Test Pack | • Run T11, T12, T13. |  | All pass. | Johanna | Not started
S2-13 | S2 | Launch | Open the front door | Slack + Outlook | • Pin the IntakeFormUrl in #lane-people-talent as the official front door (use the announcement text in Appendix D). • HR mailbox: set an automatic reply that points to the form (inspiration: email → form, no flow needed). • Tell managers: 'Not in the intake, does not exist.' |  | Pinned; auto-reply on; announcement sent. | CJ | Not started
S2-14 | S2 | Test | First real Template I case | Live | • Process the next real extra-shift submission end to end: HR approval → Paycor single event earning → resolve → Payroll FYI. |  | Gate G2 checklist complete. | Johanna | Not started
S3-01 | S3 | Decisions | Approval matrix sign-off | Stakeholders | • Get written sign-off on who approves B, C, F by region. |  | Dependency marked Confirmed. | CJ | Not started
S3-02 | S3 | Excel | Switch on B, C, F approvals | HR Change Reference.xlsx → Change Types + Approvers | • ApprovalChain: B = 'Manager > Regional', C = 'Manager > Regional > HR', F = 'Manager'. • Add Approvers rows per region. |  | Next B request starts a Manager approval (no flow edit needed). | CJ | Not started
S3-03 | S3 | Flow 6 | Create 'HR Change - 6 Checklist Progress' | Automated cloud flow | • Trigger: When an item is created or modified · List: HR Change Requests. Trigger condition below. Trigger Settings → Concurrency control ON, degree 1. • Try: Compose 'Lines', Filter 'Open steps', Filter 'Done steps', Compose 'Progress', Compose 'Next action', Condition 'Changed' → Update item + Condition 'Just finished' → Comment pattern 'Ready' + Slack. Then Catch. • Compare-before-write: the flow only updates when something changed, so its own update ends the loop after one extra run. | Trigger condition: @not(empty(triggerBody()?['Checklist'])) Lines (Compose): split(replace(triggerBody()?['Checklist'], decodeUriComponent('%0D'), ''), decodeUriComponent('%0A')) Open steps — From / advanced: outputs('Lines') · @startsWith(trim(item()), '[ ]') Done steps — From / advanced: outputs('Lines') · @startsWith(toLower(trim(item())), '[x]') Progress (Compose): if(equals(add(length(body('Open_steps')), length(body('Done_steps'))), 0), 0, div(mul(length(body('Done_steps')), 100), add(length(body('Open_steps')), length(body('Done_steps'))))) Next action (Compose): if(empty(body('Open_steps')), '', take(trim(substring(trim(first(body('Open_steps'))), 3)), 250)) Changed — Left (fx) · is equal to · true: or(not(equals(float(outputs('Progress')), float(coalesce(triggerBody()?['ChecklistProgress'], 0)))), not(equals(outputs('Next_action'), coalesce(triggerBody()?['NextAction'], '')))) Update item — ChecklistProgress (fx) / NextAction (fx): outputs('Progress') · outputs('Next_action') Just finished — Left (fx) · is equal to · true: and(equals(outputs('Progress'), 100), less(float(coalesce(triggerBody()?['ChecklistProgress'], 0)), 100), not(equals(triggerBody()?['Status']?['Value'], '3-Resolved'))) Ready text (Compose): ☑️ All checklist steps are done — set Status to 3-Resolved to close the case (LOA: only once the return is confirmed). Slack message: :ballot_box_with_check: All steps done on <@{triggerBody()?['{Link}']}¦@{triggerBody()?['RequestId']}> — @{coalesce(triggerBody()?['Assignee']?['DisplayName'], 'owner')}, ready to resolve. | T17 passes. | Johanna | Not started
S3-04 | S3 | Test | Approval and progress tests | Test Pack | • Run T14, T15, T16, T17, T22. |  | All pass. | Johanna | Not started
S3-05 | S3 | Test | UAT with Johanna | Every path A1–I | • Submit one of each change type; work and resolve each. Log issues in the Notes column. |  | Gate G3 checklist complete. | Johanna | Not started
S4-01 | S4 | Flow 7 | Create 'HR Change - 7 Daily Digest + Cutoff Reminder' | Scheduled cloud flow — every 1 day at 8:00 (your time zone) | • Try: Settings row + Settings; Compose 'Today' and 'Today key'; Excel List rows 'Change types' (tblChangeTypes); Filter 'Sensitive types'; Select 'Sensitive codes'; SharePoint Get items 'Open requests'. | Today / Today key: convertFromUtc(utcNow(), outputs('Settings')?['TimeZone']) · formatDateTime(outputs('Today'), 'yyyyMMdd') Sensitive types — From / advanced: outputs('Change_types')?['body/value'] · @equals(item()?['Sensitive'], 'Yes') Sensitive codes — Select From / Map (text mode): body('Sensitive_types') · item()?['Code'] Open requests — Filter Query / Order By / Top Count: Status ne '3-Resolved' · SLADueDate asc · 5000 | Run manually: Open requests returns your test items. | Johanna | Not started
S4-02 | S4 | Flow 7 | Digest sections | Inside Try | • Five Filter arrays named exactly as below (From fx outputs('Open_requests')?['body/value']), and one Select per filter named '<filter> lines' (e.g. 'SLA overdue lines', From fx body('SLA_overdue')) using the same Map. Then Condition 'Weekday with news' → Slack post to the People Ops room. | Unassigned: @equals(item()?['Status']?['Value'], '0-New') SLA overdue: @and(not(empty(item()?['SLADueDate'])), less(formatDateTime(item()?['SLADueDate'], 'yyyyMMdd'), outputs('Today_key'))) Action due: @and(not(empty(item()?['NextActionDue'])), lessOrEquals(formatDateTime(item()?['NextActionDue'], 'yyyyMMdd'), outputs('Today_key'))) Exceptions: @not(empty(item()?['AutomationNote'])) LOA returns: @and(startsWith(coalesce(item()?['ChangeType']?['Value'], ''), 'G '), not(empty(item()?['EndDate'])), lessOrEquals(ticks(item()?['EndDate']), ticks(addDays(utcNow(), 7)))) Line Map for every Select (text mode): concat('• <', item()?['{Link}'], '¦', item()?['RequestId'], '> ', first(split(item()?['ChangeType']?['Value'], ' ')), ' — ', if(contains(body('Sensitive_codes'), first(split(item()?['ChangeType']?['Value'], ' '))), '(confidential)', item()?['EmployeeName']), ' — ', coalesce(item()?['Assignee']?['DisplayName'], 'unassigned'), if(empty(item()?['NextAction']), '', concat(' — next: ', item()?['NextAction']))) Weekday with news — Left (fx) · is equal to · true: and(greater(dayOfWeek(outputs('Today')), 0), less(dayOfWeek(outputs('Today')), 6), greater(add(add(add(length(body('Unassigned')), length(body('SLA_overdue'))), add(length(body('Action_due')), length(body('Exceptions')))), length(body('LOA_returns'))), 0)) Slack message: :bar_chart: *HR Change — daily check* (@{length(outputs('Open_requests')?['body/value'])} open) @{if(empty(body('Unassigned_lines')), '', concat('*:white_circle: 0-New, not picked up*', decodeUriComponent('%0A'), join(body('Unassigned_lines'), decodeUriComponent('%0A')), decodeUriComponent('%0A')))}@{if(empty(body('SLA_overdue_lines')), '', concat('*:red_circle: SLA overdue*', decodeUriComponent('%0A'), join(body('SLA_overdue_lines'), decodeUriComponent('%0A')), decodeUriComponent('%0A')))}@{if(empty(body('Action_due_lines')), '', concat('*:large_yellow_circle: Next action due*', decodeUriComponent('%0A'), join(body('Action_due_lines'), decodeUriComponent('%0A')), decodeUriComponent('%0A')))}@{if(empty(body('Exceptions_lines')), '', concat('*:warning: Automation exceptions*', decodeUriComponent('%0A'), join(body('Exceptions_lines'), decodeUriComponent('%0A')), decodeUriComponent('%0A')))}@{if(empty(body('LOA_returns_lines')), '', concat('*:calendar: LOA returns within 7 days*', decodeUriComponent('%0A'), join(body('LOA_returns_lines'), decodeUriComponent('%0A'))))} | T18 passes. | Johanna | Not started
S4-03 | S4 | Flow 7 | Payroll cutoff reminder | Inside Try | • Compose 'Cutoff days'; Select 'This month cutoffs' and 'Next month cutoffs' (Map text mode); Filter 'Remind today'; Condition (length > 0) → Slack post to the managers channel. Then Catch (email only). | Cutoff days (Compose): createArray(int(outputs('Settings')?['CutoffDay1']), int(outputs('Settings')?['CutoffDay2'])) This month cutoffs — Map: formatDateTime(addDays(startOfMonth(outputs('Today')), sub(item(), 1)), 'yyyy-MM-dd') Next month cutoffs — Map: formatDateTime(addDays(startOfMonth(addToTime(outputs('Today'), 1, 'Month')), sub(item(), 1)), 'yyyy-MM-dd') Remind today — From (fx): union(body('This_month_cutoffs'), body('Next_month_cutoffs')) Remind today — advanced: @equals(formatDateTime(outputs('Today'), 'yyyy-MM-dd'), formatDateTime(addDays(addDays(item(), mul(int(outputs('Settings')?['ReminderBusinessDays']), -1)), if(equals(dayOfWeek(addDays(item(), mul(int(outputs('Settings')?['ReminderBusinessDays']), -1))), 6), -1, if(equals(dayOfWeek(addDays(item(), mul(int(outputs('Settings')?['ReminderBusinessDays']), -1))), 0), -2, 0))), 'yyyy-MM-dd')) Slack message (managers): :alarm_clock: *Payroll cutoff is @{formatDateTime(first(body('Remind_today')), 'dddd, MMM d')}.* Any extra shifts or fractional FTE pickups to report for this pay period? Submit them as *I — Fractional FTE / Extra Shift Pickup*: <@{outputs('Settings')?['IntakeFormUrl']}¦HR change request form> | T19 passes. | Johanna | Not started
S4-04 | S4 | Test | Exception drill | Flow 1 | • Run T20: make one action fail on purpose, confirm the alert, the Automation Note and the digest Exceptions line, then undo. |  | T20 = Pass. | Johanna | Not started
S4-05 | S4 | Operate | Two weeks of steady operation | Views + digest | • Use the digest every morning. Redirect any request raised in DMs/email to the form. • End of week 2: review All Open by SLA and Recently Resolved for the SLA baseline. |  | Gate G4 checklist complete. | CJ | Not started
S5-01 | S5 | Downstream | Jira ticket for offboarding (A1/A2) | New flow or a branch in Flow 1 | • When the IT dependency is confirmed: on A1/A2 create → Jira 'Create a new issue' (access revocation + equipment retrieval) → write the issue URL to JiraLink → comment. • In the Checklists table set Auto = 'jira' on the 'Create Jira ticket' steps and tick them in the same flow. |  | A test A1 creates a Jira issue and fills Jira Ticket Link. | CJ | Not started
S5-02 | S5 | Downstream | Offboarding distro email | Flow 1 branch | • When the distro address is confirmed: A1 → email the distro at intake. A2 stays manual (timing-sensitive access revocation). |  | Test A1 emails the distro. | CJ | Not started
S5-03 | S5 | Downstream | Word letters | Word Online (Business) → Populate a Microsoft Word template (premium) | • Termination letter (A2), comp change confirmation (C), job change confirmation (B). Save to the HR file; attach to the item. |  | Generated letter opens correctly. | CJ | Not started
S5-04 | S5 | Downstream | Monday.com payroll board + backfill link | Monday connector | • When the board/column is confirmed: post A1/A2 final pay and C rate changes to the payroll board; send the backfill form link to the manager on A1. |  | Item appears on the board. | CJ | Not started
S6-01 | S6 | Run | Manager self-service form | Microsoft Forms → flow → same list | • Scoped types (e.g. E, F, I), readiness checklist first. |  |  | CJ | Not started
S6-02 | S6 | Run | Dashboard | List views → Power BI (optional) | • Open by age, SLA compliance, change-type breakdown. |  |  | CJ | Not started
S6-03 | S6 | Run | In-Slack approvals | Bot token | • Replace email approvals with Slack buttons once the bot token is approved. |  |  | CJ | Not started
S6-04 | S6 | Run | Paycor write-back | Paycor iPaaS | • Auto-write approved changes instead of manual entry. |  |  | CJ | Not started
S6-05 | S6 | Run | Holiday-aware SLA | Reference workbook | • Add a tblHolidays table and skip those dates in Flow 1. |  |  | CJ | Not started

## Reusable Blocks
Reusable blocks
Built the same way in several flows. The steps say 'add the … block'.
Block | Action / field | Value / expression
Standard opening block | Settings row (Excel Online (Business) → List rows present in a table) | Location: your People Ops site · Document Library: Documents · File: HR Change/HR Change Reference.xlsx · Table: tblSettings
Standard opening block | Settings (Compose) | first(outputs('Settings_row')?['body/value'])
Standard opening block | Code (Compose) | first(split(triggerBody()?['ChangeType']?['Value'], ' '))
Standard opening block | Change type row (Excel → List rows present in a table) — Table: tblChangeTypes · Filter Query: | Code eq '@{outputs('Code')}'
Standard opening block | Config (Compose) | first(outputs('Change_type_row')?['body/value'])
Standard opening block | Request ID (Compose) | concat(outputs('Settings')?['RequestPrefix'], formatNumber(triggerBody()?['ID'], '000000'))
Comment pattern (post to the item's thread) | <Name> text (Compose) — type the message; insert @{…} parts with fx | e.g. 📥 @{outputs('Request_ID')} received.
Comment pattern (post to the item's thread) | Post <name> (SharePoint → Send an HTTP request to SharePoint) — Method | POST
Comment pattern (post to the item's thread) | Uri | _api/web/lists/getbytitle('HR Change Requests')/items(@{triggerBody()?['ID']})/Comments
Comment pattern (post to the item's thread) | Headers | Accept = application/json;odata=nometadata · Content-Type = application/json;odata=nometadata
Comment pattern (post to the item's thread) | Body (fx) | setProperty(json('{}'), 'text', take(outputs('<Name>_text'), 1900))
Try / Catch pattern | Catch (Control → Scope) → ⋯ → Configure run after | Try: ☑ has failed ☑ has timed out (☐ is successful)
Try / Catch pattern | Failure alert (Office 365 Outlook → Send an email (V2)) — To | your admin email (type it — don't depend on Settings here)
Try / Catch pattern | Subject | [HR Change] @{workflow()?['tags']?['flowDisplayName']} failed
Try / Catch pattern | Body | Open the failed run: @{concat('https://make.powerautomate.com/environments/', workflow()?['tags']?['environmentName'], '/flows/', workflow()?['name'], '/runs/', workflow()?['run']?['name'])}
Try / Catch pattern | Flag the item (SharePoint → Update item, item-triggered flows only) — AutomationNote (fx) | concat('⚠️ ', workflow()?['tags']?['flowDisplayName'], ' failed ', formatDateTime(utcNow(), 'yyyy-MM-dd HH:mm'), ' UTC — see admin email')

## Gates
Gates
Every line must be Passed before the next sprint starts.
Sprint | Gate | Criterion | Status | Date | Evidence / notes
S0 | G0 — Ready to build | D3, D5, D6 confirmed by CJ | Not started
S0 | G0 — Ready to build | Field list signed off with Johanna | Not started
S0 | G0 — Ready to build | Reference workbook uploaded and Settings filled | Not started
S0 | G0 — Ready to build | List built: all columns, choices, required fields, show/hide formulas, views | Not started
S0 | G0 — Ready to build | T21 passed (non-HR account sees only own requests) | Not started
S1 | G1 — Plumbing proven | T01–T06 pass | Not started
S1 | G1 — Plumbing proven | One live E submission by Johanna closed end to end | Not started
S1 | G1 — Plumbing proven | A failure alert email received from a Catch block (any test) | Not started
S1 | G1 — Plumbing proven | Flows owned by the HR/service account, not a personal one | Not started
S2 | G2 — Front door live | T07–T13 pass | Not started
S2 | G2 — Front door live | First real I case approved, earning entered, resolved, Payroll FYI posted | Not started
S2 | G2 — Front door live | Form pinned in #lane-people-talent; manager comms sent | Not started
S2 | G2 — Front door live | HR mailbox auto-reply points to the form | Not started
S3 | G3 — Approvals live | Approval matrix signed off; Approvers table filled per region | Not started
S3 | G3 — Approvals live | T14–T17 and T22 pass | Not started
S3 | G3 — Approvals live | UAT with Johanna on every path A1–I | Not started
S4 | G4 — Operational | T18–T20 pass | Not started
S4 | G4 — Operational | Two weeks of digests reviewed | Not started
S4 | G4 — Operational | No request handled outside the list in those two weeks | Not started
S4 | G4 — Operational | SLA baseline reviewed (All Open by SLA / Recently Resolved) | Not started
S5 | G5 — per item | Dependency confirmed in writing | Not started
S5 | G5 — per item | Built and tested on a test request | Not started
S5 | G5 — per item | Checklist step updated to show it is automated (Auto column) | Not started
S6 | Ongoing | Each item ships with its own test cases and a rollback note | Not started

## Test Pack
Test Pack (UAT)
Run in the sprint shown. Record the result.
ID | Sprint | Scenario | How | Expected | Result | Tested by | Date | Notes
T01 | S1 | E — basic intake | Submit an E request on a weekday. | Request = 'E — Personal Data Change — <name>'; Request ID HRC-00000N; SLA = next business day; 📥 comment; People Ops Slack ping; confirmation email. | Not run
T02 | S1 | Weekend SLA | Submit an E request on Saturday (or check SLA Start in the run of a Friday-evening test). | Saturday submission → SLA = Tuesday (counting starts Monday). | Not run
T03 | S1 | E checklist | Look at the T01 item. | Checklist has 5 '[ ] 0n.' lines; 03–05 end with '⚙ resolution'; Next Action = '01. Confirm field(s) changing and new value'; 📋 comment lists the steps. | Not run
T04 | S1 | Other — catch-all | Submit Change Type = Other. | No checklist; '⚠️ … needs manual scoping' comment; Slack warning. | Not run
T05 | S1 | Resolve E | Set Assignee = you, Status = 3-Resolved. | Completion Date = today; Outcome = Completed; 03–05 ticked [x]; '✅ Resolved on <date> by <you>' (+ note if 01–02 were open); close-the-loop email. | Not run
T06 | S1 | Live E | Johanna submits and works a real E request. | Same as T01–T05 with no manual fixes. | Not run
T07 | S2 | I — HR approval (approve) | Submit I: Rate Type Hourly, $100, first date worked in the current pay period before cutoff. | 2-Waiting / Pending / Waiting On Approver; HR approval email; approve → Approved, step 01 [x], 🔓 comment; Status 0-New (no Assignee) or 1-Assigned. | Not run
T08 | S2 | I — after cutoff | Submit I with first date worked in a pay period whose cutoff has passed. | Pay Period label set; Submitted After Cutoff = Yes; ⚠️ in comment and Slack. | Not run
T09 | S2 | I — HR rejects | Submit I; reject with a comment. | Status 3-Resolved; Outcome Rejected; open steps [–]; rejection email with approval notes; NO Payroll FYI. | Not run
T10 | S2 | I — Payroll FYI | Resolve the T07 request. | Payroll room message once; Payroll Notified On = today; editing the item again does not re-post. | Not run
T11 | S2 | G — LOA | Submit G with an expected return date. | SLA blank ('Per policy' in comment); Assignee = CJ; Slack shows '(confidential — see list)'; ticking every step does not resolve it. | Not run
T12 | S2 | A1 — voluntary offboarding | Submit A1 with Last Day next Friday. | SLA Due Date = Last Day; 16 steps; 'Terminate in Paycor' line shows 📅 <last day>. | Not run
T13 | S2 | A2 — involuntary (sensitive) | Submit A2. | Name withheld in Slack and the digest; SLA = Last Day; 12 steps. | Not run
T14 | S3 | B — two-stage approval | Submit B (Manager = you, Region with a Regional row). | Manager approval first; Regional only after it is approved; both lines in Approval History. | Not run
T15 | S3 | C — reject at stage 2 | Submit C; approve Manager, reject Regional. | HR stage never sent; Rejected path as in T09. | Not run
T16 | S3 | No approver | Submit B with a Region that has no Regional row and with the '*' row set Active = No. | Approval Status = Needs approver; Status 2-Waiting; Slack alert. (Restore the '*' row.) | Not run
T17 | S3 | Checklist progress | On any open request change two '[ ]' to '[x]'; then tick the rest. | Checklist % updates; Next Action = next open step; at 100%: '☑️ … ready to resolve' comment + Slack; Status unchanged. | Not run
T18 | S4 | Daily digest | Run Flow 7 manually with open test items (one overdue, one 0-New, one exception). | One Slack post with the right sections; A2/G names show '(confidential)'. | Not run
T19 | S4 | Cutoff reminder | Temporarily set CutoffDay1 to a date ReminderBusinessDays business days from today; run Flow 7. | Managers channel reminder with the form link. Restore the setting. | Not run
T20 | S4 | Exception drill | Temporarily point Flow 1's Slack step at a channel the service account can't post to; submit E. | Admin email with run link; Automation Note filled; item in the Exceptions view and digest. Undo. | Not run
T21 | S0 | Permissions | A non-HR colleague submits a request, then browses the list and searches for another employee's request. | They see only their own item. | Not run
T22 | S3 | Config without flow edits | Change E's SLABusinessDays to 2 in Excel; submit E. | SLA = 2 business days. Restore to 1. | Not run

## Decisions
Decisions
Design decisions and the ones that need your confirmation.
ID | Topic | Decision | Why | Status
D1 | System of record | Replace the HR Change Slack List with ONE SharePoint list: HR Change Requests. | Your direction. One place per case; filterable views; works with Power Automate natively. | Decided
D2 | Reference data | SLAs, approval chains, checklists, approvers and settings live as tables in one Excel workbook (HR Change Reference.xlsx) that the flows read. | Manage them like a reference sheet, without extra lists or flow edits. Contract: never rename a table or a column header. | Decided
D3 | Front door | The list's New form is the front door, pinned in #lane-people-talent. Microsoft Forms is reserved for the Phase 3 manager self-service form. | A Slack Workflow Builder form cannot write to SharePoint without a bot token or webhook app. Principle update: 'Microsoft-native for the record, Slack for visibility'. | Confirm (CJ)
D4 | Checklist / subtasks | The checklist is posted to the item's comment thread (the work log) AND written to an editable Checklist field. HR ticks [ ] → [x]; a flow keeps Checklist % and Next Action current. | Delivers Phase 1 (thread checklist) and the Phase 2 goal (progress visibility) without a second list. | Decided
D5 | Template I — Payroll role | Payroll is a verifier, not a gate: a one-way Slack FYI when People Ops resolves an I case. | The plan's Flow 3 section says this explicitly; the master reference's 'Payroll final approval' line conflicts. To make Payroll a gate later, add 'Payroll' to I's ApprovalChain. | Confirm (CJ)
D6 | Manager field | 'Manager Name' becomes a Manager person field. | Approvals need an email to route to. | Confirm (Johanna)
D7 | Comp 'approval confirmed (Y/N)' | Retired. Replaced by the in-system approval chain. | One source of truth for approval. | Decided
D8 | Approvals channel | Power Automate Approvals (email, Teams, Power Automate app). In-Slack approve buttons wait for the Phase 3 bot token. | Standard connector, no IT app approval. | Decided
D9 | Slack connection | Power Automate Slack connector (OAuth) under a People Ops service account. Posts go to channels. | Answers the plan's open question: no bot token needed. DMs need member IDs, so channels for now. | Decided
D10 | Status model | Keep Tag, You're It (0-New, 1-Assigned, 2-Waiting, 3-Resolved). Add Waiting On, Next Action, Next Action Due, Outcome. | Keeps continuity; adds 'who/what/when' for every active case (from the inspiration). | Decided
D11 | Sensitive change types | A2 and G (and optionally H) withhold the employee name from Slack and the digest. Item-level permissions on the list. | Limit sensitive content in notifications. | Decided
D12 | SLA calendar | Business days skip weekends, not holidays. | Simple first. Holiday table is on the Run-phase backlog. | Accepted
D13 | Approval rollout | I's HR approval goes live in Sprint 2 (pilot). B, C, F chains are switched on in Sprint 3 by filling ApprovalChain in Excel after the matrix is signed off. | Matches the dependency 'Approval matrix signed off by stakeholders'. | Decided
D14 | Plan typo | 'deparHRent' → 'department' (looks like a find/replace of 'tm' → 'HR'). Check the source doc for other damaged words. |  | FYI
D15 | Template I pilot cases | The ICS live examples (DVA $100/hr, $800/day, first days Aug 15) have passed. Pilot with the next real I submission. |  | FYI

## Inspiration Review
Inspiration Review
What we adopted, adapted, deferred or rejected from the email-ticketing inspiration — and why.
Idea | Verdict | Why | How it shows up
Email-first intake (employees keep emailing HR) | Reject | Breaks 'One front door' and 'Not in the intake, does not exist'. | Adapt instead: an auto-reply on the HR mailbox that points people to the form (Sprint 2, no flow needed).
Ticket-marker matching on email replies | Reject (for now) | Only needed with email intake. | The earlier hr-ticketing-triage solution keeps this if email intake is ever wanted.
One accountable owner + Next action + Next action date on every active case | Adopt | Directly improves Tag, You're It: 'In progress' alone doesn't say what happens next. | Next Action / Next Action Due fields; Flow 6 keeps Next Action = first open checklist step.
Richer status set (waiting on employee / third party) | Adapt | Keep the 0–3 labels for continuity. | Add a Waiting On field used with 2-Waiting.
First human response date | Defer | Your SLAs measure completion, not first response. | Revisit in Run phase for reporting.
Action-based workbench views | Adopt | Fast daily triage. | 8 views (see Views tab), incl. Needs Attention Today and Exceptions.
Daily digest instead of per-update emails | Adopt | Less noise; one place to see risk. | Flow 7 (Sprint 4), sensitive names withheld.
Separate restricted lane for sensitive casework | Adapt | HR change requests are mostly routine; LOA/offboarding need care, ER investigations are out of scope. | Sensitive flag per change type + item-level permissions now; restricted ER area is a Run-phase decision.
Copy email bodies/attachments into the ticket; Ticket Messages list | Reject | One-list rule; the comment thread is the log. | Attachments go on the list item directly when needed.
Send HR responses from list fields | Reject | Complexity and risk for little gain. | Reply in Slack/Outlook; close-the-loop email is automated at resolution.
Auto-close after inactivity | Reject | LOA must stay open; closure is a deliberate HR act in your plan. | Daily digest surfaces stale items instead.
Exception path — never lose a request | Adopt | A failed step must stay visible. | Try/Catch in every flow: admin email with run link + Automation Note + Exceptions view.
Loop guards with trigger conditions | Adopt | Flows that update the item they trigger on can loop. | Flows 3, 4, 6 use trigger conditions / compare-before-write.
Don't promise resolution dates in auto-acknowledgements | Adopt | Sets the right expectation. | Confirmation email says 'target completion' and 'a team member will pick it up'.
Pilot scenario test list (duplicates, out-of-office, failures…) | Adapt | Email-specific cases don't apply. | 22-case Test Pack written for HR change paths, approvals, permissions and failures.
Test access with a non-HR account before launch | Adopt | Filtered views are not security. | Gate 0 / test T21.

## Plan Traceability
Plan Traceability
Every element of the project plan and where it is delivered.
Project plan item | Where it lives in the build | Sprint
Guiding principle — One front door | List New form pinned in #lane-people-talent; HR mailbox auto-reply points to it | S0, S2
Guiding principle — Not in the intake, does not exist | Every case is an item; digest + views only show list items | S2
Guiding principle — Slack native first | Updated (D3): Microsoft-native for the record, Slack for visibility | S0
Guiding principle — The list is the system of record | ONE SharePoint list: HR Change Requests | S0
Guiding principle — Templates do the thinking | Checklists table (A1–I) → Flow 2 Checklist Router | S1
Guiding principle — The thread is the work log | Item Comments: intake, checklist, approvals, resolution all logged | S1
Guiding principle — Offboarding is a path | A1/A2 are change types on the same list and engine | S2
Layer 1 — Intake form + confirmation to submitter | List form + Flow 1 Intake Notification (confirmation email, People Ops ping) | S1
Layer 2 / Phase 1 — Thread-based checklist | Flow 2 posts the checklist as an item comment | S1
Layer 2 / Phase 2 — True subtasks + progress | Checklist field with [ ]/[x] + Flow 6 Checklist % and Next Action | S3
Master template items never completed | Checklists table in the reference workbook (SOP source of truth) | S0
Layer 3 — Email sends | Flow 1 confirmation, Flow 4 close-the-loop | S1
Layer 3 — Slack notifications | Flows 1, 2, 3, 5, 6, 7 | S1–S4
Layer 3 — Jira, Word templates, Monday.com | Sprint 5, each behind its dependency gate | S5
Intake fields — universal + conditional | List columns + show/hide formulas (List Fields tab) | S0
List fields — Request ID … Completion date | List columns (List Fields tab) | S0
Status labels 0–3 | Status choice (Statuses tab) | S0
SLA targets by change type | Change Types table → Flow 1 SLA Due Date (business days / last day / per policy) | S1
Completion auto-comment (✅ Resolved on [date] by [assignee] + stamp date) | Flow 4 Completion Auto-Comment | S1
Flow 1 — Intake Notification | Flow 1 | S1
Flow 2 — Checklist Router (10 paths + Other catch-all) | Flow 2 (one generic path reads the table; Other → 'needs manual scoping') | S1
Flow 3 — Payroll Notification (Template I only, not a gate) | Flow 3 | S2
Template I — HR approval → Paycor earning → resolve | Flow 5 (HR stage) + checklist I + Flow 3 | S2
Template I — log against the right pay period; flag after cutoff | Flow 1 Pay Period + Submitted After Cutoff | S2
Template G — route to CJ, stays open until return | Default Assignee = CJ; Flow 6 never auto-resolves; digest flags returns | S2, S4
Approval routing (B, C, F per approval matrix) | Flow 5 + Approvers table; switched on after matrix sign-off | S3
Nice to add — cutoff reminder to managers | Flow 7 cutoff reminder | S4
Phase 3 — Dashboard view | Views (All Open by SLA, Recently Resolved) + daily digest; Power BI later | S4, S6
Phase 3 — Manager self-service form | Microsoft Forms → same list (scoped types) | S6
Phase 3 — Bot token / in-Slack approvals; Paycor iPaaS | Run-phase backlog | S6
Build order — E first, then I, then G | Sprint 1 = E end-to-end; Sprint 2 = I pilot then G | S1, S2
Open question — Slack app vs Power Automate connector | Answered: connector (D9) | S0

## Dependencies
Dependencies
From the plan's dependencies table, plus what this build adds.
Item | Owner | Status | Needed by | Notes
HR Change Reference.xlsx stored on the People Ops site | CJ | Ready (this kit) | S0 | Flows read it.
Slack connection under a People Ops service account | CJ / IT | To confirm | S0 | Messages appear from this account.
Field list signed off | Johanna | To confirm | S0 | Gate 0.
Approval matrix signed off by stakeholders | CJ | To confirm | S3 | Gate 3: switches on B, C, F approvals.
Jira connector access in Power Automate + HR Jira project | IT | To confirm | S5 | Plan open question.
Shared offboarding email distro exists and is current | CJ / Johanna | To confirm | S5 | Plan open question.
Word termination letter template (content controls) | CJ | To build | S5 | 'Populate a Microsoft Word template' is a premium connector action.
Monday backfill request form URL | Talent | To confirm | S5
Payroll Monday board — column/item to post to | Sydney / Sandra | To confirm | S5 | Plan open question.
Paycor bot token / iPaaS | IT / Paycor CSM | Pending | S6 | Run phase.

## Comms
Launch comms (Sprint 2)
Replace <IntakeFormUrl> with the real link.
Where | Text
#lane-people-talent announcement (pin it) | 📣 *New: one front door for HR changes* From today, every HR change request (offboarding, job/status, comp, pay/banking, personal data, time/PTO, LOA, benefits, extra shifts) goes through this form: <IntakeFormUrl> • You'll get a confirmation with a request ID and a target date. • If it needs approval, the approver gets it automatically. • You'll hear back when it's done. Requests sent by DM or email will be pointed back here — if it isn't in the intake, we can't track it. Thank you! — People Ops
HR mailbox automatic reply | Thanks for reaching out to People Ops. HR change requests are handled through our request form so nothing gets lost: <IntakeFormUrl>. For anything else, a member of the team will reply soon.