## Overview
HR Change + Orchestration — Build Blueprint
Sprints, gates and progress. Mint cells are inputs; everything else is calculated.
Sprint 0 start date | 2026-10-08 | ← type your real start date (a Monday)
Sprint | Name | Phase | Weeks | Start | End | Steps | Done | % done | Gate | Gate status
S0 | Foundations | Crawl | 1 | 2026-10-08 | 2026-10-14 | 11 | 0 | 0% | G0 — Ready to build | Not started
S1 | Crawl — DATA path end to end | Crawl | 2 | 2026-10-15 | 2026-10-28 | 22 | 0 | 0% | G1 — Plumbing proven | Not started
S2 | Crawl complete — XPAY pilot + front door live | Crawl | 2 | 2026-10-29 | 2026-11-11 | 9 | 0 | 0% | G2 — Front door live | Not started
S3 | Walk — approval chains + UAT | Walk | 2 | 2026-11-12 | 2026-11-25 | 4 | 0 | 0% | G3 — Approvals live | Not started
S4 | Walk — daily digest, cutoff reminder, hardening | Walk | 2 | 2026-11-26 | 2026-12-09 | 5 | 0 | 0% | G4 — Operational | Not started
S5 | Walk — downstream actions (dependency-driven) | Walk | 2 | 2026-12-10 | 2026-12-23 | 4 | 0 | 0% | G5 — per item | Not started
S6 | Run — full audit + integrations | Run | 0 | 2026-12-24 |  | 5 | 0 | 0% | Ongoing | Not started
Total | [5 empty] | 60 | 0 | 0%
How to use this workbook:
1. Set the start date above. Sprint dates follow (S6 is ongoing).
2. Work the 'Build Steps' tab top to bottom. Set Status as you go — progress updates here.
3. Each sprint ends at a gate (Gates tab). Don't start the next sprint until every gate line is Passed.
4. Run the tests named in each sprint (Test Pack tab). Record Pass/Fail.
5. The Word document 'HR Change Blueprint' has the same steps with full explanations.
Formulas:
Start = IF([End, row above]="","",[End, row above]+1)
End = IF(OR([Start]="",[Weeks]=0),"",[Start]+[Weeks]*7-1)

## Roadmap
Roadmap — sprints and gates
Crawl → Walk → Run, as in the project plan.
Sprint | Name | Phase | Start | End | Goal | Entry criteria | Gate | Gate criteria
S0 | Foundations | Crawl | 2026-10-08 | 2026-10-14 | Reference workbook, the one list, the form, views, connections. | Plan approved; this kit downloaded. | G0 — Ready to build | • D3, D4, D5 confirmed by CJ • Change types, InfoNeeded wording and checklists reviewed with Johanna • Reference workbook uploaded and Settings filled • List built (core columns, choices, views); form built and not yet shared • T21 passed (a non-HR colleague can submit the form but can't open the list)
S1 | Crawl — DATA path end to end | Crawl | 2026-10-15 | 2026-10-28 | Flow 0 Form Intake, Flow 1 Intake Notification, Flow 2 Checklist Router, Flow 3 Case Updates, Flow 4 Close-out. Proven on DATA. | G0 passed. | G1 — Plumbing proven | • T01–T06 pass • One live DATA request by Johanna closed end to end • A failure alert received from a Catch block • Flows owned by the service account, not a personal one
S2 | Crawl complete — XPAY pilot + front door live | Crawl | 2026-10-29 | 2026-11-11 | Flow 5 Approval Routing (HR stage for XPAY), Payroll FYI, LOA/offboarding checks, front door launch. | G1 passed. | G2 — Front door live | • T07–T13 pass • First real XPAY case approved, earning entered, closed, Payroll FYI posted • Form pinned in #lane-people-talent; announcement sent • HR mailbox auto-reply points to the form
S3 | Walk — approval chains + UAT | Walk | 2026-11-12 | 2026-11-25 | JOB, COMP, PTO (and REQ) chains switched on from Excel; UAT across every type. | G2 passed; approval matrix signed off. | G3 — Approvals live | • Matrix signed off; Approvers table filled per region • T14–T17 and T22 pass • UAT with Johanna on every change type
S4 | Walk — daily digest, cutoff reminder, hardening | Walk | 2026-11-26 | 2026-12-09 | Flow 6; exception drill; two weeks of steady operation. | G3 passed. | G4 — Operational | • T18–T20 pass • Two weeks of digests reviewed • No request handled outside the list in those two weeks • First-response and SLA baseline reviewed (views)
S5 | Walk — downstream actions (dependency-driven) | Walk | 2026-12-10 | 2026-12-23 | Jira, offboarding distro, Word letters, Monday board — each when its dependency is confirmed. | G4 passed; dependency confirmed. | G5 — per item | • Dependency confirmed in writing • Built and tested on a test request • Checklist step marked automated (Auto column)
S6 | Run — full audit + integrations | Run | 2026-12-24 |  | Dashboard, in-Slack approvals, Paycor iPaaS, holiday-aware SLA. | G5 items as available. | Ongoing | • Each item ships with its own tests and a rollback note

## Build Steps
Build Steps
Every step in order. Status is the only column you need to update (plus Done on / Notes).
ID | Sprint | Area | Step | Where | Do | Paste / settings | Check | Owner | Status | Done on | Notes
S0-01 | S0 | Decisions | Confirm the open design decisions | Decisions tab | • Review D3 (Microsoft Form front door, HR-only list), D4 (general change types), D5 (XPAY: Payroll verifier, not gate). • Mark each Confirmed or Changed. |  | D3, D4, D5 no longer say 'Confirm'. | CJ | Not started
S0-02 | S0 | Excel | Store the reference workbook | People Ops SharePoint site → Documents | • Create a folder 'HR Change' and upload HR Change Reference.xlsx. Folder → Manage access: HR owners edit; nobody else needs access. • Read the About sheet: never rename a table (tblSettings, tblChangeTypes, tblChecklist, tblApprovers) or a column header. |  | The file opens in Excel for the web; Table Design shows the four table names. | CJ | Not started
S0-03 | S0 | Excel | Fill in Settings | HR Change Reference.xlsx → Settings | • Set TimeZone, CutoffDay1/2 (real payroll cutoffs), ReminderBusinessDays, ServiceAccountEmail, AdminEmail. FormUrl comes in S0-10. |  | No '<' placeholders left except FormUrl. | Johanna | Not started
S0-04 | S0 | Excel | Review Change Types with Johanna | HR Change Reference.xlsx → Change Types | • Check every type's Group, DefaultPriority, SLA, DueDateRule and InfoNeeded wording (it goes into the form subtitle and the confirmation email). • Retire a type by deleting its row and its choice; add one by adding a row (Code = the text before ' — '). • Leave ApprovalChain blank for JOB, COMP, PTO, REQ until Sprint 3 (D13). XPAY = 'HR' (pilot). • Set DefaultAssigneeEmail where a type always goes to the same person (LOA and ER → CJ are pre-filled). |  | Every row has Code, ChangeType, DueDateRule; Yes/No columns contain only Yes or No. | Johanna | Not started
S0-05 | S0 | Excel | Review the sub-step checklists | HR Change Reference.xlsx → Checklists | • Walk each type's steps. Keep Step as two digits (01, 02 …). Auto: 'approval' / 'resolution' steps tick themselves. AfterApproval = Yes shows 🔒. |  | Johanna signs off each type's steps. | Johanna | Not started
S0-06 | S0 | Excel | Draft the Approvers table | HR Change Reference.xlsx → Approvers | • Rows for Regional / HR / Payroll by Region ('*' = any region). Region values must match the list's Region choices. |  | An active HR row with Region '*' exists (needed for the XPAY pilot). | CJ | Not started
S0-07 | S0 | SharePoint | Create the list from CSV | Site → + New → List → From CSV → HR-Change-Requests.csv | • Keep the headers exactly (no spaces = the internal names the flows use). Set types per the List Fields tab. • Name it 'HR Change Requests' → Create. Delete the SAMPLE row. • Add the Person column AssignedTo (type the name without spaces; rename the display name later if you like). • Paste the full choice lists into ChangeType, Priority, Status, Region, WaitingOn, ApprovalStatus, Outcome. Defaults: Status 0-New, ApprovalStatus Not required. • Rename display names to the List Fields tab's 'Display name' (e.g. ChangeType → Category, RequestId → Ticket Reference). |  | List settings → Columns: internal names have no spaces (hover a column: Field=EmployeeName). | Johanna | Not started
S0-08 | S0 | SharePoint | Make the list HR-only | List settings → Permissions for this list | • Stop inheriting permissions. Keep HR team (Edit or above) and the service account; remove everyone else. • Nobody else needs access: requesters use the form and get emails. |  | Test T21. | CJ | Not started
S0-09 | S0 | SharePoint | Create the workbench views | List → All Items → Create new view | • Create the 8 views on the Views tab. |  | 'Needs Attention Today' and 'Exceptions' exist. | Johanna | Not started
S0-10 | S0 | Forms | Build the 'HR Request' form | forms.office.com → New Form | • Settings: 'Only people in my organization can respond' + 'Record name'. • Add the 8 questions from the Form Questions tab, in order. Question 1's choices = the Category values exactly (copy from Change Types → ChangeType). • Details subtitle: paste the wording from the Form Questions tab. Optionally list each type's InfoNeeded under it. • Copy the form link (Collect responses → Copy link) into Settings → FormUrl. Don't share it yet. |  | Preview: all 8 questions; question 1 shows all 17 categories. | Johanna | Not started
S0-11 | S0 | Power Automate | Create the connections | make.powerautomate.com → Data → Connections | • Sign in as the People Ops service account for SharePoint, Excel Online (Business), Office 365 Outlook, Office 365 Users, Microsoft Forms, Approvals and Slack (D11). • Make sure that account owns the form (or is a form co-owner) so Flow 0 can read responses. |  | Seven connections show 'Connected' under the service account. | CJ | Not started
S1-01 | S1 | Flow 0 | Create 'HR Change - 0 Form Intake' | My flows → + New flow → Automated cloud flow | • Trigger: Microsoft Forms — When a new response is submitted · Form: HR Request. • Add Scope 'Try'. Inside: Microsoft Forms → Get response details 'Response' (Form + Response Id from the trigger); Office 365 Users → Get user profile (V2) 'Requester' (User = Responders' Email). • SharePoint → Create item 'Create request' in HR Change Requests with the fields below (pick each answer from 'Response' in Dynamic content). • Below Try: the Catch pattern (no 'Flag the item' — there is no item yet). | Title: Dynamic content 'What do you need?', then type ' — ', then 'Employee name' (Flow 1 rewrites it anyway) ChangeType Value: answer: What do you need? EmployeeName / EmployeeId / ManagerEmail: answers 2, 3, 4 Region Value: answer 5 EffectiveDate: answer 6 Priority Value (fx) — blank when unanswered; inside fx, click answer 7 in Dynamic content where it says <answer 7>: if(empty(<answer 7>), null, <answer 7>) Description: answer 8 RequesterEmail: Responders' Email (from Response) RequesterName: Display Name (from Requester) | Submit the form once: a new list item appears with these fields. | Johanna | Not started
S1-02 | S1 | Flow 1 | Create 'HR Change - 1 Intake Notification' | Automated cloud flow | • Trigger: SharePoint — When an item is created · List: HR Change Requests. (Runs for form requests AND items HR adds by hand.) • Add Scope 'Try' and the Standard opening block inside it (Appendix A). | Settings row (Excel Online (Business) → List rows present in a table): Location: People Ops site · Document Library: Documents · File: HR Change/HR Change Reference.xlsx · Table: tblSettings Settings (Compose): first(outputs('Settings_row')?['body/value']) Code (Compose): first(split(triggerBody()?['ChangeType']?['Value'], ' ')) Change type row (Excel → List rows present in a table) — Table: tblChangeTypes · Filter Query:: Code eq '@{outputs('Code')}' Config (Compose): first(outputs('Change_type_row')?['body/value']) Request ID (Compose): concat(outputs('Settings')?['RequestPrefix'], formatNumber(triggerBody()?['ID'], '000000')) | Run once with a DATA request: Config shows the DATA row. | Johanna | Not started
S1-03 | S1 | Flow 1 | SLA due date | Inside Try, after Request ID | • Four Compose actions. | Submitted Local: convertFromUtc(triggerBody()?['Created'], outputs('Settings')?['TimeZone']) SLA Start (weekend submissions start Monday): addDays(startOfDay(outputs('Submitted_Local')), if(equals(dayOfWeek(outputs('Submitted_Local')), 6), 2, if(equals(dayOfWeek(outputs('Submitted_Local')), 0), 1, 0))) SLA Days: if(empty(outputs('Config')?['SLABusinessDays']), 0, int(outputs('Config')?['SLABusinessDays'])) SLA Due Date: if(equals(outputs('Config')?['DueDateRule'], 'Effective date'), formatDateTime(triggerBody()?['EffectiveDate'], 'yyyy-MM-dd'), if(equals(outputs('SLA_Days'), 0), null, formatDateTime(addDays(outputs('SLA_Start'), add(add(mul(div(outputs('SLA_Days'), 5), 7), mod(outputs('SLA_Days'), 5)), if(greater(add(dayOfWeek(outputs('SLA_Start')), mod(outputs('SLA_Days'), 5)), 5), 2, 0))), 'yyyy-MM-dd'))) | DATA submitted Monday → SLA Due Date = Tuesday. | Johanna | Not started
S1-04 | S1 | Flow 1 | Pay period + cutoff flag (XPAY) | Inside Try | • Three Compose actions. Effective Date = first date worked for XPAY. | Pay Period: concat(formatDateTime(triggerBody()?['EffectiveDate'], 'yyyy-MM'), if(lessOrEquals(dayOfMonth(triggerBody()?['EffectiveDate']), 15), ' (1-15)', ' (16-EOM)')) Cutoff Date: addDays(startOfMonth(triggerBody()?['EffectiveDate']), sub(int(if(lessOrEquals(dayOfMonth(triggerBody()?['EffectiveDate']), 15), outputs('Settings')?['CutoffDay1'], outputs('Settings')?['CutoffDay2'])), 1)) After Cutoff: and(equals(outputs('Code'), 'XPAY'), greater(ticks(outputs('Submitted_Local')), ticks(addDays(outputs('Cutoff_Date'), 1)))) | For DATA: After Cutoff = false. | Johanna | Not started
S1-05 | S1 | Flow 1 | Write the core fields back | Inside Try → SharePoint → Update item | • List: HR Change Requests · Id: ID (trigger). Required columns it asks for: pick the same field from the trigger. • Don't set Status or ApprovalStatus here — column defaults cover intake; Flow 5 owns approvals. | Title (fx): concat(triggerBody()?['ChangeType']?['Value'], ' — ', triggerBody()?['EmployeeName']) RequestId (fx): outputs('Request_ID') Priority Value (fx): coalesce(triggerBody()?['Priority']?['Value'], outputs('Config')?['DefaultPriority'], 'Routine') ReceivedDate (fx): triggerBody()?['Created'] SLADueDate (fx) / NextActionDue (fx): outputs('SLA_Due_Date') · outputs('SLA_Due_Date') RequesterEmail (fx) — keeps form value; falls back to whoever created the item: coalesce(triggerBody()?['RequesterEmail'], triggerBody()?['Author']?['Email']) RequesterName (fx): coalesce(triggerBody()?['RequesterName'], triggerBody()?['Author']?['DisplayName']) | Item shows Ticket Reference HRC-00000N, Priority, Received Date, SLA Due Date. | Johanna | Not started
S1-06 | S1 | Flow 1 | Default assignee | Inside Try → Condition 'Default assignee?' | • Left (fx) and(empty(triggerBody()?['AssignedTo']), not(empty(coalesce(outputs('Config')?['DefaultAssigneeEmail'], '')))) · is equal to · (fx) true • True → Update item 'Set default assignee' (required columns from trigger). | AssignedTo Claims (fx): outputs('Config')?['DefaultAssigneeEmail'] | An LOA request gets CJ as Assigned To. | Johanna | Not started
S1-07 | S1 | Flow 1 | Intake comment | Inside Try — Comment pattern (Appendix B) named 'Intake' | • Add 'Display Name' first (Slack uses it too). | Display Name (Compose): if(equals(outputs('Config')?['Sensitive'], 'Yes'), '(confidential — see list)', triggerBody()?['EmployeeName']) Intake text (Compose): 📥 @{outputs('Request_ID')} received from @{coalesce(triggerBody()?['RequesterName'], triggerBody()?['Author']?['DisplayName'])}. Priority: @{coalesce(triggerBody()?['Priority']?['Value'], outputs('Config')?['DefaultPriority'])}. SLA target: @{coalesce(outputs('SLA_Due_Date'), outputs('Config')?['SLATarget'])}. Info needed for this type: @{outputs('Config')?['InfoNeeded']}@{if(equals(outputs('Code'), 'XPAY'), concat(decodeUriComponent('%0A'), 'Pay period: ', outputs('Pay_Period'), if(outputs('After_Cutoff'), ' ⚠️ submitted after the payroll cutoff', '')), '')} Post intake — Body (fx): setProperty(json('{}'), 'text', take(outputs('Intake_text'), 1900)) | Comment in the item's Comments pane. | Johanna | Not started
S1-08 | S1 | Flow 1 | Ping the People Ops room | Inside Try → Slack → Post message (V2) | • Channel: People Ops room. | Message text: :inbox_tray: *New HR request <@{triggerBody()?['{Link}']}¦@{outputs('Request_ID')}>* — @{coalesce(triggerBody()?['Priority']?['Value'], outputs('Config')?['DefaultPriority'])} @{triggerBody()?['ChangeType']?['Value']} — @{outputs('Display_Name')} Effective @{formatDateTime(triggerBody()?['EffectiveDate'], 'MMM d, yyyy')} • SLA target @{coalesce(outputs('SLA_Due_Date'), outputs('Config')?['SLATarget'])}@{if(outputs('After_Cutoff'), ' • :warning: after payroll cutoff', '')} | Posts; for OFF-I / LOA / ER the name shows '(confidential — see list)'. | Johanna | Not started
S1-09 | S1 | Flow 1 | Confirmation to the requester | Inside Try → Office 365 Outlook → Send an email (V2) | • Lists what HR needs for this request type, without promising a date. | To (fx): coalesce(triggerBody()?['RequesterEmail'], triggerBody()?['Author']?['Email']) Subject: We've got your request: @{outputs('Request_ID')} Body: Hi @{coalesce(triggerBody()?['RequesterName'], triggerBody()?['Author']?['DisplayName'])}, Thanks for using the HR front door. Your request @{outputs('Request_ID')} (@{triggerBody()?['ChangeType']?['Value']}) is in the People Ops queue. To finish it we'll need: @{outputs('Config')?['InfoNeeded']}. If anything's missing from what you sent, just reply to this email. Target: @{coalesce(outputs('SLA_Due_Date'), outputs('Config')?['SLATarget'])}. This is an automatic confirmation — a team member will pick it up and keep you posted. People Ops | Email arrives with the InfoNeeded line. | Johanna | Not started
S1-10 | S1 | Flow 1 | Catch block + test | Below Try | • Catch pattern (Appendix C). Run T01 and T02. | Catch (Control → Scope) → ⋯ → Configure run after: Try: ☑ has failed ☑ has timed out (☐ is successful) Failure alert (Office 365 Outlook → Send an email (V2)) — To: your admin email (type it — don't depend on Settings here) Subject: [HR Change] @{workflow()?['tags']?['flowDisplayName']} failed Body: Open the failed run: @{concat('https://make.powerautomate.com/environments/', workflow()?['tags']?['environmentName'], '/flows/', workflow()?['name'], '/runs/', workflow()?['run']?['name'])} Flag the item (SharePoint → Update item, item-triggered flows only) — AutomationNote (fx): concat('⚠️ ', workflow()?['tags']?['flowDisplayName'], ' failed ', formatDateTime(utcNow(), 'yyyy-MM-dd HH:mm'), ' UTC — see admin email') | T01, T02 = Pass. | Johanna | Not started
S1-11 | S1 | Flow 2 | Create 'HR Change - 2 Checklist Router' | Automated cloud flow | • Trigger: When an item is created · List: HR Change Requests. Separate from Flow 1 on purpose: one failing can't stop the other. • Scope 'Try' + Standard opening block. | Settings row (Excel Online (Business) → List rows present in a table): Location: People Ops site · Document Library: Documents · File: HR Change/HR Change Reference.xlsx · Table: tblSettings Settings (Compose): first(outputs('Settings_row')?['body/value']) Code (Compose): first(split(triggerBody()?['ChangeType']?['Value'], ' ')) Change type row (Excel → List rows present in a table) — Table: tblChangeTypes · Filter Query:: Code eq '@{outputs('Code')}' Config (Compose): first(outputs('Change_type_row')?['body/value']) Request ID (Compose): concat(outputs('Settings')?['RequestPrefix'], formatNumber(triggerBody()?['ID'], '000000')) | Saved. | Johanna | Not started
S1-12 | S1 | Flow 2 | Read this type's sub-steps | Inside Try | • Excel List rows 'Checklist rows' (tblChecklist); Filter array 'Active steps'. | Checklist rows — Filter Query / Order By: Code eq '@{outputs('Code')}' · Step Active steps — From (fx) / advanced: outputs('Checklist_rows')?['body/value'] · @equals(item()?['Active'], 'Yes') | For DATA: 5 rows. | Johanna | Not started
S1-13 | S1 | Flow 2 | Write and post the checklist | Inside Try → Condition 'Has checklist' | • Left (fx) length(body('Active_steps')) · is greater than · 0. True branch: two Selects (Map in text mode), one Compose, Update item, Comment pattern 'Checklist comment'. | Checklist lines — From / Map: body('Active_steps') · concat('[ ] ', item()?['Step'], '. ', item()?['Task'], if(equals(item()?['AfterApproval'], 'Yes'), ' 🔒', ''), if(equals(item()?['DueOnLastDay'], 'Yes'), concat(' 📅 ', formatDateTime(triggerBody()?['EffectiveDate'], 'MMM d')), ''), if(empty(item()?['Auto']), '', concat(' ⚙ ', item()?['Auto']))) Comment lines — From / Map: body('Active_steps') · concat('☐ ', item()?['Step'], '. ', item()?['Task'], if(empty(item()?['Details']), '', concat(' — ', item()?['Details']))) Checklist text (Compose): join(body('Checklist_lines'), decodeUriComponent('%0A')) Save checklist (Update item) — Checklist / ChecklistProgress / NextAction: outputs('Checklist_text') · 0 · concat(first(body('Active_steps'))?['Step'], '. ', first(body('Active_steps'))?['Task']) Checklist comment text (Compose): 📋 @{outputs('Code')} sub-steps — @{length(body('Active_steps'))}. Tick them in the Checklist field by changing [ ] to [x]. @{join(body('Comment_lines'), decodeUriComponent('%0A'))} Post checklist comment — Body (fx): setProperty(json('{}'), 'text', take(outputs('Checklist_comment_text'), 1900)) | DATA item: 5 '[ ]' lines; Next Action = '01. …'; checklist comment posted. | Johanna | Not started
S1-14 | S1 | Flow 2 | Catch-all for OTHER | Condition 'Has checklist' → False | • Comment pattern 'No template' + Slack post. Then Catch block below Try. Run T03, T04. | No template text (Compose): ⚠️ No sub-steps for @{outputs('Code')} — needs manual scoping. Assign it and write the steps into the Checklist field ([ ] one per line). Slack message: :warning: <@{triggerBody()?['{Link}']}¦@{outputs('Request_ID')}> (@{triggerBody()?['ChangeType']?['Value']}) needs manual scoping. Catch (Control → Scope) → ⋯ → Configure run after: Try: ☑ has failed ☑ has timed out (☐ is successful) Failure alert (Office 365 Outlook → Send an email (V2)) — To: your admin email (type it — don't depend on Settings here) Subject: [HR Change] @{workflow()?['tags']?['flowDisplayName']} failed Body: Open the failed run: @{concat('https://make.powerautomate.com/environments/', workflow()?['tags']?['environmentName'], '/flows/', workflow()?['name'], '/runs/', workflow()?['run']?['name'])} Flag the item (SharePoint → Update item, item-triggered flows only) — AutomationNote (fx): concat('⚠️ ', workflow()?['tags']?['flowDisplayName'], ' failed ', formatDateTime(utcNow(), 'yyyy-MM-dd HH:mm'), ' UTC — see admin email') | T03, T04 = Pass. | Johanna | Not started
S1-15 | S1 | Flow 3 | Create 'HR Change - 3 Case Updates' | Automated cloud flow | • Trigger: When an item is created or modified · List: HR Change Requests. Trigger Settings → Concurrency control ON, degree 1. • Purpose: stamps First Human Response, keeps Checklist % and Next Action in step with the ticks. Compare-before-write ends its own loop after one extra run. • Scope 'Try': Settings row + Settings, then the composes below. | First response needed (Compose): and(empty(triggerBody()?['FirstResponseDate']), not(equals(triggerBody()?['Status']?['Value'], '0-New')), not(equals(toLower(triggerBody()?['Editor']?['Email']), toLower(outputs('Settings')?['ServiceAccountEmail'])))) Lines (Compose): split(replace(coalesce(triggerBody()?['Checklist'], ''), decodeUriComponent('%0D'), ''), decodeUriComponent('%0A')) Open steps / Done steps (Filter arrays on Lines): @startsWith(trim(item()), '[ ]') · @startsWith(toLower(trim(item())), '[x]') Progress (Compose): if(equals(add(length(body('Open_steps')), length(body('Done_steps'))), 0), 0, div(mul(length(body('Done_steps')), 100), add(length(body('Open_steps')), length(body('Done_steps'))))) Progress changed (Compose): not(equals(float(outputs('Progress')), float(coalesce(triggerBody()?['ChecklistProgress'], 0)))) Checklist next (Compose): if(empty(body('Open_steps')), '', take(trim(substring(trim(first(body('Open_steps'))), 3)), 250)) Next action (Compose) — HR's own text sticks until the next tick: if(or(outputs('Progress_changed'), empty(triggerBody()?['NextAction'])), outputs('Checklist_next'), triggerBody()?['NextAction']) | Saved. | Johanna | Not started
S1-16 | S1 | Flow 3 | Write only when something changed | Inside Try → Condition 'Changed' | • Left (fx) below · is equal to · (fx) true → Update item (required columns from trigger) → Condition 'Just finished' → Comment pattern 'Ready' + Slack. Then Catch. | Changed — Left: or(outputs('First_response_needed'), outputs('Progress_changed'), not(equals(outputs('Next_action'), coalesce(triggerBody()?['NextAction'], '')))) Update — FirstResponseDate (fx): if(outputs('First_response_needed'), utcNow(), triggerBody()?['FirstResponseDate']) Update — ChecklistProgress / NextAction: outputs('Progress') · outputs('Next_action') Just finished — Left (· is equal to · true): and(outputs('Progress_changed'), equals(outputs('Progress'), 100), not(equals(triggerBody()?['Status']?['Value'], '3-Resolved'))) Ready text (Compose): ☑️ All sub-steps are done — set Status to 3-Resolved to close (LOA: only once the return is confirmed). Slack message: :ballot_box_with_check: All steps done on <@{triggerBody()?['{Link}']}¦@{triggerBody()?['RequestId']}> — @{coalesce(triggerBody()?['AssignedTo']?['DisplayName'], 'owner')}, ready to resolve. Catch (Control → Scope) → ⋯ → Configure run after: Try: ☑ has failed ☑ has timed out (☐ is successful) Failure alert (Office 365 Outlook → Send an email (V2)) — To: your admin email (type it — don't depend on Settings here) Subject: [HR Change] @{workflow()?['tags']?['flowDisplayName']} failed Body: Open the failed run: @{concat('https://make.powerautomate.com/environments/', workflow()?['tags']?['environmentName'], '/flows/', workflow()?['name'], '/runs/', workflow()?['run']?['name'])} Flag the item (SharePoint → Update item, item-triggered flows only) — AutomationNote (fx): concat('⚠️ ', workflow()?['tags']?['flowDisplayName'], ' failed ', formatDateTime(utcNow(), 'yyyy-MM-dd HH:mm'), ' UTC — see admin email') | T17 passes. | Johanna | Not started
S1-17 | S1 | Flow 4 | Create 'HR Change - 4 Close-out' | Automated cloud flow | • Trigger: When an item is created or modified · List: HR Change Requests. Trigger conditions (2 lines): fires once per closure — the flow stamps Closed Date, so its own update can't re-fire it. • Scope 'Try' + opening block (skip Request ID). | Trigger condition 1: @equals(triggerBody()?['Status']?['Value'], '3-Resolved') Trigger condition 2: @empty(triggerBody()?['ClosedDate']) Settings row (Excel Online (Business) → List rows present in a table): Location: People Ops site · Document Library: Documents · File: HR Change/HR Change Reference.xlsx · Table: tblSettings Settings (Compose): first(outputs('Settings_row')?['body/value']) Code (Compose): first(split(triggerBody()?['ChangeType']?['Value'], ' ')) Change type row (Excel → List rows present in a table) — Table: tblChangeTypes · Filter Query:: Code eq '@{outputs('Code')}' Config (Compose): first(outputs('Change_type_row')?['body/value']) | Saved. | Johanna | Not started
S1-18 | S1 | Flow 4 | Outcome, resolver and ticked checklist | Inside Try | • Composes, one Select, one Filter array. | Outcome / Resolver: coalesce(triggerBody()?['Outcome']?['Value'], 'Completed') · coalesce(triggerBody()?['AssignedTo']?['DisplayName'], triggerBody()?['Editor']?['DisplayName']) Today: convertFromUtc(utcNow(), outputs('Settings')?['TimeZone']) Checklist before: split(replace(coalesce(triggerBody()?['Checklist'], ''), decodeUriComponent('%0D'), ''), decodeUriComponent('%0A')) Checklist after — From / Map: outputs('Checklist_before') · if(and(startsWith(item(), '[ ]'), or(contains(item(), '⚙ resolution'), not(equals(outputs('Outcome'), 'Completed')))), concat(if(equals(outputs('Outcome'), 'Completed'), '[x]', '[–]'), substring(item(), 3)), item()) Still open — From / advanced: body('Checklist_after') · @startsWith(item(), '[ ]') | On a DATA close: steps 03–05 become [x]. | Johanna | Not started
S1-19 | S1 | Flow 4 | Stamp Closed Date and post ✅ | Inside Try | • Update item 'Stamp close' (required columns from trigger), then Comment pattern 'Resolved'. | ClosedDate / Outcome Value: formatDateTime(outputs('Today'), 'yyyy-MM-dd') · outputs('Outcome') Checklist (fx): if(empty(triggerBody()?['Checklist']), '', join(body('Checklist_after'), decodeUriComponent('%0A'))) NextAction: '' Resolved text (Compose): ✅ Resolved on @{formatDateTime(outputs('Today'), 'MMM d, yyyy')} by @{outputs('Resolver')}@{if(equals(outputs('Outcome'), 'Completed'), '', concat(' (Outcome: ', outputs('Outcome'), ')'))}@{if(greater(length(body('Still_open')), 0), concat(' — note: ', string(length(body('Still_open'))), ' sub-step(s) were still open'), '')} | Comment reads '✅ Resolved on <date> by <assignee>'. | Johanna | Not started
S1-20 | S1 | Flow 4 | Close-the-loop + People Ops summary | Inside Try | • Condition 'Close the loop?' → Send an email (V2). Condition 'Summary?' → Slack People Ops room. | Close the loop? — Left (· is equal to · true): or(equals(outputs('Config')?['CloseLoopEmail'], 'Yes'), not(equals(outputs('Outcome'), 'Completed'))) Email To / Subject: coalesce(triggerBody()?['RequesterEmail'], triggerBody()?['Author']?['Email']) · Update on your HR request @{triggerBody()?['RequestId']} Email Body: Hi @{triggerBody()?['RequesterName']}, @{if(equals(outputs('Outcome'), 'Completed'), concat('Good news — your request ', triggerBody()?['RequestId'], ' (', triggerBody()?['ChangeType']?['Value'], ') is complete.'), concat('Your request ', triggerBody()?['RequestId'], ' (', triggerBody()?['ChangeType']?['Value'], ') was closed as ', outputs('Outcome'), '. Your HR contact will follow up with the details.'))} Questions? Reply to this email or ask in #lane-people-talent. People Ops Summary? — Left: equals(outputs('Config')?['PostSummaryToPeopleOps'], 'Yes') Slack summary: :white_check_mark: *<@{triggerBody()?['{Link}']}¦@{triggerBody()?['RequestId']}>* @{outputs('Code')} closed by @{outputs('Resolver')} (@{outputs('Outcome')}).@{if(greater(length(body('Still_open')), 0), concat(' :warning: ', string(length(body('Still_open'))), ' step(s) still open.'), '')} | T05 passes. | Johanna | Not started
S1-21 | S1 | Flow 4 | Payroll FYI (plan Flow 3) + Catch | Inside Try → Condition 'Payroll FYI?' | • Left (fx) and(equals(outputs('Config')?['NotifyPayrollOnClose'], 'Yes'), equals(outputs('Outcome'), 'Completed')) · is equal to · true → Slack post to the Payroll room. One-way — never waits for Payroll (D5). • Below Try: Catch pattern. (The Payroll part is tested in Sprint 2, T10.) | Slack message (Payroll room): :moneybag: *Extra pay submitted in Paycor* — <@{triggerBody()?['{Link}']}¦@{triggerBody()?['RequestId']}> Employee: @{triggerBody()?['EmployeeName']} (@{triggerBody()?['EmployeeId']}) • First date worked: @{formatDateTime(triggerBody()?['EffectiveDate'], 'MMM d, yyyy')} • Pay period: @{concat(formatDateTime(triggerBody()?['EffectiveDate'], 'yyyy-MM'), if(lessOrEquals(dayOfMonth(triggerBody()?['EffectiveDate']), 15), ' (1-15)', ' (16-EOM)'))} Details: @{take(coalesce(triggerBody()?['Description'], ''), 600)} _FYI — please verify the earning in Paycor. No response needed._ Catch (Control → Scope) → ⋯ → Configure run after: Try: ☑ has failed ☑ has timed out (☐ is successful) Failure alert (Office 365 Outlook → Send an email (V2)) — To: your admin email (type it — don't depend on Settings here) Subject: [HR Change] @{workflow()?['tags']?['flowDisplayName']} failed Body: Open the failed run: @{concat('https://make.powerautomate.com/environments/', workflow()?['tags']?['environmentName'], '/flows/', workflow()?['name'], '/runs/', workflow()?['run']?['name'])} Flag the item (SharePoint → Update item, item-triggered flows only) — AutomationNote (fx): concat('⚠️ ', workflow()?['tags']?['flowDisplayName'], ' failed ', formatDateTime(utcNow(), 'yyyy-MM-dd HH:mm'), ' UTC — see admin email') | Saved. | Johanna | Not started
S1-22 | S1 | Test | Run the Sprint 1 tests | Test Pack | • T05, T06 (and re-run T01–T04 if anything changed). |  | Gate G1 checklist complete. | Johanna | Not started
S2-01 | S2 | Flow 5 | Create 'HR Change - 5 Approval Routing' | Automated cloud flow | • Trigger: When an item is created · List: HR Change Requests. • BEFORE Try (variables can't live in a scope): Initialize variable 'Outcome' (String) = Approved; 'History' (String) = empty. • Scope 'Try' + opening block, then Filter array 'Stages' and Condition 'Needs approval' (Left fx length(body('Stages')) · is greater than · 0). Everything below goes in its True branch. | Settings row (Excel Online (Business) → List rows present in a table): Location: People Ops site · Document Library: Documents · File: HR Change/HR Change Reference.xlsx · Table: tblSettings Settings (Compose): first(outputs('Settings_row')?['body/value']) Code (Compose): first(split(triggerBody()?['ChangeType']?['Value'], ' ')) Change type row (Excel → List rows present in a table) — Table: tblChangeTypes · Filter Query:: Code eq '@{outputs('Code')}' Config (Compose): first(outputs('Change_type_row')?['body/value']) Request ID (Compose): concat(outputs('Settings')?['RequestPrefix'], formatNumber(triggerBody()?['ID'], '000000')) Stages — From (fx) / advanced: split(replace(coalesce(outputs('Config')?['ApprovalChain'], ''), ' ', ''), '>') · @not(empty(item())) | XPAY → Stages = ["HR"]; DATA → empty, nothing happens. | Johanna | Not started
S2-02 | S2 | Flow 5 | Mark waiting and loop the stages | Needs approval → True | • Excel List rows 'Approvers rows' (tblApprovers). Update item 'Mark pending'. Apply to each 'Each stage' over body('Stages') — ⚠️ Settings → Concurrency ON, degree 1. • Inside the loop: Condition 'Still approved' (variables('Outcome') is equal to Approved); S2-03 and S2-04 go in its True branch. | Mark pending — ApprovalStatus / Status / WaitingOn: Pending · 2-Waiting · Approver | Item shows 2-Waiting / Pending / Approver. | Johanna | Not started
S2-03 | S2 | Flow 5 | Find the approver | Still approved → True | • Filter arrays 'This region' / 'Any region' (From fx outputs('Approvers_rows')?['body/value']), Compose 'Approver'. | This region — advanced: @and(equals(item()?['Role'], items('Each_stage')), equals(item()?['Active'], 'Yes'), equals(toLower(trim(item()?['Region'])), toLower(trim(coalesce(triggerBody()?['Region']?['Value'], ''))))) Any region — advanced: @and(equals(item()?['Role'], items('Each_stage')), equals(item()?['Active'], 'Yes'), equals(trim(item()?['Region']), '*')) Approver (Compose): if(equals(items('Each_stage'), 'Manager'), coalesce(triggerBody()?['ManagerEmail'], ''), coalesce(first(body('This_region'))?['ApproverEmail'], first(body('Any_region'))?['ApproverEmail'], '')) | XPAY: Approver = the HR row's email. | Johanna | Not started
S2-04 | S2 | Flow 5 | Ask, record, stop on reject | Condition 'Approver found' (Left fx empty(outputs('Approver')) · is equal to · false) | • True: Update item 'Show approver'; Approvals → Start and wait for an approval 'Approval' (Approve/Reject – First to respond); Append to string variable 'History'; Comment pattern 'Decision'; Condition 'Rejected?' (outputs('Approval')?['body/outcome'] is equal to Reject) → Set variable Outcome = Rejected. • False: Set variable Outcome = NoApprover; Slack alert to the People Ops room. | Show approver — CurrentApprover: @{items('Each_stage')}: @{outputs('Approver')} Approval — Title / Assigned to: @{items('Each_stage')} approval: @{triggerBody()?['ChangeType']?['Value']} — @{triggerBody()?['EmployeeName']} [@{outputs('Request_ID')}] · outputs('Approver') Approval — Details: **Employee:** @{triggerBody()?['EmployeeName']} (@{triggerBody()?['EmployeeId']}) **Request:** @{triggerBody()?['ChangeType']?['Value']} • effective @{formatDateTime(triggerBody()?['EffectiveDate'], 'MMM d, yyyy')} **Requested by:** @{triggerBody()?['RequesterName']} @{triggerBody()?['Description']} Approval — Item link / description: triggerBody()?['{Link}'] · Open @{outputs('Request_ID')} History — value (end with Enter): @{formatDateTime(convertFromUtc(utcNow(), outputs('Settings')?['TimeZone']), 'yyyy-MM-dd')} @{items('Each_stage')} @{if(equals(outputs('Approval')?['body/outcome'], 'Approve'), 'approved', 'rejected')} by @{first(outputs('Approval')?['body/responses'])?['responder']?['displayName']}@{if(empty(first(outputs('Approval')?['body/responses'])?['comments']), '', concat(' — ', first(outputs('Approval')?['body/responses'])?['comments']))} Decision text (Compose): @{if(equals(outputs('Approval')?['body/outcome'], 'Approve'), '👍', '👎')} @{items('Each_stage')} @{if(equals(outputs('Approval')?['body/outcome'], 'Approve'), 'approved', 'rejected')} by @{first(outputs('Approval')?['body/responses'])?['responder']?['displayName']} No approver — Slack message: :rotating_light: <@{triggerBody()?['{Link}']}¦@{outputs('Request_ID')}> needs a *@{items('Each_stage')}* approver but none was found (Manager email empty, or no active Approvers row for this role/region). | Approval email arrives; decision comment appears. | Johanna | Not started
S2-05 | S2 | Flow 5 | Save the result after the loop | Needs approval → True, AFTER the loop | • SharePoint Get item 'Request now'. Select 'Approval ticks'. Update item 'Save approval result' (required columns from Request now). Comment pattern 'Result'. Then Catch below Try. | Approval ticks — From / Map: split(replace(coalesce(outputs('Request_now')?['body/Checklist'], ''), decodeUriComponent('%0D'), ''), decodeUriComponent('%0A')) · if(and(startsWith(item(), '[ ]'), contains(item(), '⚙ approval')), concat('[x]', substring(item(), 3)), item()) ApprovalStatus Value: if(equals(variables('Outcome'), 'Approved'), 'Approved', if(equals(variables('Outcome'), 'Rejected'), 'Rejected', 'Needs approver')) Status Value: if(equals(variables('Outcome'), 'Rejected'), '3-Resolved', if(equals(variables('Outcome'), 'NoApprover'), '2-Waiting', if(empty(outputs('Request_now')?['body/AssignedTo']), '0-New', '1-Assigned'))) Outcome Value / WaitingOn Value: if(equals(variables('Outcome'), 'Rejected'), 'Rejected', outputs('Request_now')?['body/Outcome']?['Value']) · if(equals(variables('Outcome'), 'NoApprover'), 'Approver', null) CurrentApprover / InternalNotes: '' · concat(coalesce(outputs('Request_now')?['body/InternalNotes'], ''), decodeUriComponent('%0A'), variables('History')) Checklist: if(or(equals(variables('Outcome'), 'NoApprover'), empty(outputs('Request_now')?['body/Checklist'])), outputs('Request_now')?['body/Checklist'], join(body('Approval_ticks'), decodeUriComponent('%0A'))) Result text (Compose): @{if(equals(variables('Outcome'), 'Approved'), concat('🔓 Approved (', join(body('Stages'), ' → '), '). 🔒 steps can start now.'), if(equals(variables('Outcome'), 'Rejected'), '⛔ Rejected — closed as Rejected; the requester will be told.', '⚠️ Approval stopped: no approver found. Fix the manager email or the Approvers table, approve offline and log it in Internal Notes.'))} Catch (Control → Scope) → ⋯ → Configure run after: Try: ☑ has failed ☑ has timed out (☐ is successful) Failure alert (Office 365 Outlook → Send an email (V2)) — To: your admin email (type it — don't depend on Settings here) Subject: [HR Change] @{workflow()?['tags']?['flowDisplayName']} failed Body: Open the failed run: @{concat('https://make.powerautomate.com/environments/', workflow()?['tags']?['environmentName'], '/flows/', workflow()?['name'], '/runs/', workflow()?['run']?['name'])} Flag the item (SharePoint → Update item, item-triggered flows only) — AutomationNote (fx): concat('⚠️ ', workflow()?['tags']?['flowDisplayName'], ' failed ', formatDateTime(utcNow(), 'yyyy-MM-dd HH:mm'), ' UTC — see admin email') | T07: after approving, Approval Status = Approved and step 01 is [x]. | Johanna | Not started
S2-06 | S2 | Test | XPAY pilot tests | Test Pack | • Run T07, T08, T09, T10. |  | All pass. | Johanna | Not started
S2-07 | S2 | Test | LOA, offboarding and ER paths | Test Pack | • Run T11, T12, T13. |  | All pass. | Johanna | Not started
S2-08 | S2 | Launch | Open the front door | Slack + Outlook | • Pin the FormUrl in #lane-people-talent with the announcement (Appendix D). • HR mailbox: automatic reply pointing to the form. • Tell managers: 'Not in the intake, does not exist.' |  | Pinned; auto-reply on; announcement sent. | CJ | Not started
S2-09 | S2 | Test | First real XPAY case | Live | • Next real extra-shift request end to end: HR approval → Paycor single event earning → close → Payroll FYI. |  | Gate G2 checklist complete. | Johanna | Not started
S3-01 | S3 | Decisions | Approval matrix sign-off | Stakeholders | • Written sign-off on who approves JOB, COMP, PTO, REQ by region. |  | Dependency Confirmed. | CJ | Not started
S3-02 | S3 | Excel | Switch on the approval chains | HR Change Reference.xlsx → Change Types + Approvers | • ApprovalChain: JOB = 'Manager > Regional', COMP = 'Manager > Regional > HR', PTO = 'Manager' (REQ as signed off). • Add Approvers rows per region. |  | Next JOB request starts a Manager approval (no flow edit). | CJ | Not started
S3-03 | S3 | Test | Approval and config tests | Test Pack | • Run T14, T15, T16, T17, T22. |  | All pass. | Johanna | Not started
S3-04 | S3 | Test | UAT with Johanna | Every change type | • Submit one of each type through the form; work and close each. Log issues in Notes. |  | Gate G3 checklist complete. | Johanna | Not started
S4-01 | S4 | Flow 6 | Create 'HR Change - 6 Daily Digest + Cutoff Reminder' | Scheduled cloud flow — every 1 day at 8:00 (your time zone) | • Try: Settings row + Settings; Compose 'Today' and 'Today key'; Excel List rows 'Change types'; Filter 'Sensitive types'; Select 'Sensitive codes'; SharePoint Get items 'Open requests'. | Today / Today key: convertFromUtc(utcNow(), outputs('Settings')?['TimeZone']) · formatDateTime(outputs('Today'), 'yyyyMMdd') Sensitive types — From / advanced: outputs('Change_types')?['body/value'] · @equals(item()?['Sensitive'], 'Yes') Sensitive codes — From / Map (text mode): body('Sensitive_types') · item()?['Code'] Open requests — Filter Query / Order By / Top Count: Status ne '3-Resolved' · SLADueDate asc · 5000 | Run manually: Open requests returns your test items. | Johanna | Not started
S4-02 | S4 | Flow 6 | Digest sections | Inside Try | • Five Filter arrays named exactly as below (From fx outputs('Open_requests')?['body/value']), and one Select per filter named '<filter> lines' (e.g. 'SLA overdue lines', From fx body('SLA_overdue')) with the same Map. Then Condition 'Weekday with news' → Slack People Ops room. | Unassigned: @equals(item()?['Status']?['Value'], '0-New') SLA overdue: @and(not(empty(item()?['SLADueDate'])), less(formatDateTime(item()?['SLADueDate'], 'yyyyMMdd'), outputs('Today_key'))) Action due: @and(not(empty(item()?['NextActionDue'])), lessOrEquals(formatDateTime(item()?['NextActionDue'], 'yyyyMMdd'), outputs('Today_key'))) Waiting: @equals(item()?['Status']?['Value'], '2-Waiting') Exceptions: @not(empty(item()?['AutomationNote'])) Line Map (text mode): concat('• <', item()?['{Link}'], '¦', item()?['RequestId'], '> ', first(split(item()?['ChangeType']?['Value'], ' ')), ' — ', if(contains(body('Sensitive_codes'), first(split(item()?['ChangeType']?['Value'], ' '))), '(confidential)', item()?['EmployeeName']), ' — ', coalesce(item()?['AssignedTo']?['DisplayName'], 'unassigned'), if(empty(item()?['WaitingOn']?['Value']), '', concat(' — waiting on ', item()?['WaitingOn']?['Value'])), if(empty(item()?['NextAction']), '', concat(' — next: ', item()?['NextAction']))) Weekday with news — Left (· is equal to · true): and(greater(dayOfWeek(outputs('Today')), 0), less(dayOfWeek(outputs('Today')), 6), greater(add(add(add(length(body('Unassigned')), length(body('SLA_overdue'))), add(length(body('Action_due')), length(body('Exceptions')))), length(body('Waiting'))), 0)) Slack message: :bar_chart: *HR requests — daily check* (@{length(outputs('Open_requests')?['body/value'])} open) @{if(empty(body('Unassigned_lines')), '', concat('*:white_circle: 0-New, not picked up*', decodeUriComponent('%0A'), join(body('Unassigned_lines'), decodeUriComponent('%0A')), decodeUriComponent('%0A')))}@{if(empty(body('SLA_overdue_lines')), '', concat('*:red_circle: SLA overdue*', decodeUriComponent('%0A'), join(body('SLA_overdue_lines'), decodeUriComponent('%0A')), decodeUriComponent('%0A')))}@{if(empty(body('Action_due_lines')), '', concat('*:large_yellow_circle: Next action due*', decodeUriComponent('%0A'), join(body('Action_due_lines'), decodeUriComponent('%0A')), decodeUriComponent('%0A')))}@{if(empty(body('Waiting_lines')), '', concat('*:hourglass: Waiting*', decodeUriComponent('%0A'), join(body('Waiting_lines'), decodeUriComponent('%0A')), decodeUriComponent('%0A')))}@{if(empty(body('Exceptions_lines')), '', concat('*:warning: Automation exceptions*', decodeUriComponent('%0A'), join(body('Exceptions_lines'), decodeUriComponent('%0A'))))} | T18 passes. | Johanna | Not started
S4-03 | S4 | Flow 6 | Payroll cutoff reminder | Inside Try | • Compose 'Cutoff days'; Select 'This month cutoffs' / 'Next month cutoffs' (Map text mode); Filter 'Remind today'; Condition (length > 0) → Slack managers channel. Then Catch (email only). | Cutoff days (Compose): createArray(int(outputs('Settings')?['CutoffDay1']), int(outputs('Settings')?['CutoffDay2'])) This month cutoffs — Map: formatDateTime(addDays(startOfMonth(outputs('Today')), sub(item(), 1)), 'yyyy-MM-dd') Next month cutoffs — Map: formatDateTime(addDays(startOfMonth(addToTime(outputs('Today'), 1, 'Month')), sub(item(), 1)), 'yyyy-MM-dd') Remind today — From (fx): union(body('This_month_cutoffs'), body('Next_month_cutoffs')) Remind today — advanced: @equals(formatDateTime(outputs('Today'), 'yyyy-MM-dd'), formatDateTime(addDays(addDays(item(), mul(int(outputs('Settings')?['ReminderBusinessDays']), -1)), if(equals(dayOfWeek(addDays(item(), mul(int(outputs('Settings')?['ReminderBusinessDays']), -1))), 6), -1, if(equals(dayOfWeek(addDays(item(), mul(int(outputs('Settings')?['ReminderBusinessDays']), -1))), 0), -2, 0))), 'yyyy-MM-dd')) Slack message (managers): :alarm_clock: *Payroll cutoff is @{formatDateTime(first(body('Remind_today')), 'dddd, MMM d')}.* Any extra shifts or additional pay to report for this pay period? Submit them as *XPAY — Extra Shift / Additional Pay*: <@{outputs('Settings')?['FormUrl']}¦HR request form> | T19 passes. | Johanna | Not started
S4-04 | S4 | Test | Exception drill | Flow 1 | • Run T20, then undo the change. |  | T20 = Pass. | Johanna | Not started
S4-05 | S4 | Operate | Two weeks of steady operation | Views + digest | • Use the digest every morning; redirect DM/email requests to the form. • End of week 2: review first-response times and SLA (All Open by SLA / Recently Closed). |  | Gate G4 checklist complete. | CJ | Not started
S5-01 | S5 | Downstream | Jira ticket for offboarding | New flow or a branch in Flow 1 | • When IT confirms: on OFF-V / OFF-I create → Jira 'Create a new issue' (access + equipment) → add the issue link to Internal Notes → comment. • Set Auto = 'jira' on the 'Create Jira ticket' steps and tick them in the same flow. |  | A test OFF-V creates a Jira issue. | CJ | Not started
S5-02 | S5 | Downstream | Offboarding distro email | Flow 1 branch | • When the distro address is confirmed: OFF-V → email the distro at intake. OFF-I stays manual (timing-sensitive). |  | Test OFF-V emails the distro. | CJ | Not started
S5-03 | S5 | Downstream | Word letters | Word Online (Business) → Populate a Microsoft Word template (premium) | • Termination letter (OFF-I), comp change (COMP) and job change (JOB) confirmations. Save to the HR file; attach to the item. |  | Generated letter opens correctly. | CJ | Not started
S5-04 | S5 | Downstream | Monday.com payroll board + backfill link | Monday connector | • When confirmed: post OFF-V / OFF-I final pay and COMP changes to the payroll board; send the backfill link on OFF-V (or raise a REQ request). |  | Item appears on the board. | CJ | Not started
S6-01 | S6 | Run | Dashboard | List views → Power BI (optional) | • Open by age, first response and SLA compliance, request-type breakdown. |  |  | CJ | Not started
S6-02 | S6 | Run | In-Slack approvals | Bot token | • Replace email approvals with Slack buttons once the bot token is approved. |  |  | CJ | Not started
S6-03 | S6 | Run | Paycor write-back | Paycor iPaaS | • Auto-write approved changes instead of manual entry. |  |  | CJ | Not started
S6-04 | S6 | Run | Holiday-aware SLA | Reference workbook | • Add tblHolidays and skip those dates in Flow 1. |  |  | CJ | Not started
S6-05 | S6 | Run | Email intake (optional) | hr-ticketing-triage solution | • If the team ever wants email intake back, add the message/conversation identifier columns and reuse the triage flow. |  |  | CJ | Not started

## Reusable Blocks
Reusable blocks
Built the same way in several flows. The steps say 'add the … block'.
Block | Action / field | Value / expression
Standard opening block | Settings row (Excel Online (Business) → List rows present in a table) | Location: People Ops site · Document Library: Documents · File: HR Change/HR Change Reference.xlsx · Table: tblSettings
Standard opening block | Settings (Compose) | first(outputs('Settings_row')?['body/value'])
Standard opening block | Code (Compose) | first(split(triggerBody()?['ChangeType']?['Value'], ' '))
Standard opening block | Change type row (Excel → List rows present in a table) — Table: tblChangeTypes · Filter Query: | Code eq '@{outputs('Code')}'
Standard opening block | Config (Compose) | first(outputs('Change_type_row')?['body/value'])
Standard opening block | Request ID (Compose) | concat(outputs('Settings')?['RequestPrefix'], formatNumber(triggerBody()?['ID'], '000000'))
Comment pattern (post to the item's thread) | <Name> text (Compose) — type the message; insert @{…} parts with fx | e.g. 📥 @{outputs('Request_ID')} received.
Comment pattern (post to the item's thread) | Post <name> (SharePoint → Send an HTTP request to SharePoint) — Method | POST
Comment pattern (post to the item's thread) | Uri | _api/web/lists/getbytitle('HR Change Requests')/items(@{triggerBody()?['ID']})/Comments
Comment pattern (post to the item's thread) | Headers | Accept = application/json;odata=nometadata · Content-Type = application/json;odata=nometadata
Comment pattern (post to the item's thread) | Body (fx) | setProperty(json('{}'), 'text', take(outputs('<Name>_text'), 1900))
Try / Catch pattern | Catch (Control → Scope) → ⋯ → Configure run after | Try: ☑ has failed ☑ has timed out (☐ is successful)
Try / Catch pattern | Failure alert (Office 365 Outlook → Send an email (V2)) — To | your admin email (type it — don't depend on Settings here)
Try / Catch pattern | Subject | [HR Change] @{workflow()?['tags']?['flowDisplayName']} failed
Try / Catch pattern | Body | Open the failed run: @{concat('https://make.powerautomate.com/environments/', workflow()?['tags']?['environmentName'], '/flows/', workflow()?['name'], '/runs/', workflow()?['run']?['name'])}
Try / Catch pattern | Flag the item (SharePoint → Update item, item-triggered flows only) — AutomationNote (fx) | concat('⚠️ ', workflow()?['tags']?['flowDisplayName'], ' failed ', formatDateTime(utcNow(), 'yyyy-MM-dd HH:mm'), ' UTC — see admin email')

## Gates
Gates
Every line must be Passed before the next sprint starts.
Sprint | Gate | Criterion | Status | Date | Evidence / notes
S0 | G0 — Ready to build | D3, D4, D5 confirmed by CJ | Not started
S0 | G0 — Ready to build | Change types, InfoNeeded wording and checklists reviewed with Johanna | Not started
S0 | G0 — Ready to build | Reference workbook uploaded and Settings filled | Not started
S0 | G0 — Ready to build | List built (core columns, choices, views); form built and not yet shared | Not started
S0 | G0 — Ready to build | T21 passed (a non-HR colleague can submit the form but can't open the list) | Not started
S1 | G1 — Plumbing proven | T01–T06 pass | Not started
S1 | G1 — Plumbing proven | One live DATA request by Johanna closed end to end | Not started
S1 | G1 — Plumbing proven | A failure alert received from a Catch block | Not started
S1 | G1 — Plumbing proven | Flows owned by the service account, not a personal one | Not started
S2 | G2 — Front door live | T07–T13 pass | Not started
S2 | G2 — Front door live | First real XPAY case approved, earning entered, closed, Payroll FYI posted | Not started
S2 | G2 — Front door live | Form pinned in #lane-people-talent; announcement sent | Not started
S2 | G2 — Front door live | HR mailbox auto-reply points to the form | Not started
S3 | G3 — Approvals live | Matrix signed off; Approvers table filled per region | Not started
S3 | G3 — Approvals live | T14–T17 and T22 pass | Not started
S3 | G3 — Approvals live | UAT with Johanna on every change type | Not started
S4 | G4 — Operational | T18–T20 pass | Not started
S4 | G4 — Operational | Two weeks of digests reviewed | Not started
S4 | G4 — Operational | No request handled outside the list in those two weeks | Not started
S4 | G4 — Operational | First-response and SLA baseline reviewed (views) | Not started
S5 | G5 — per item | Dependency confirmed in writing | Not started
S5 | G5 — per item | Built and tested on a test request | Not started
S5 | G5 — per item | Checklist step marked automated (Auto column) | Not started
S6 | Ongoing | Each item ships with its own tests and a rollback note | Not started

## Test Pack
Test Pack (UAT)
Run in the sprint shown. Record the result.
ID | Sprint | Scenario | How | Expected | Result | Tested by | Date | Notes
T01 | S1 | DATA — basic intake | Submit the form: DATA, weekday. | Item created by Flow 0; Request = 'DATA — Employee Data Update — <name>'; HRC-00000N; Priority Routine; Received Date; SLA = next business day; 📥 comment with 'Info needed'; Slack ping; confirmation email listing what's needed. | Not run
T02 | S1 | Weekend SLA | Submit DATA on Saturday (or a Friday-evening test). | Saturday submission → SLA = Tuesday. | Not run
T03 | S1 | DATA sub-steps | Look at the T01 item. | Checklist has 5 '[ ] 0n.' lines; 03–05 end with '⚙ resolution'; Next Action = '01. …'; 📋 comment lists the steps. | Not run
T04 | S1 | OTHER — catch-all | Submit OTHER. | No checklist; '⚠️ … needs manual scoping' comment; Slack warning. | Not run
T05 | S1 | Pick up, tick, close | Assign yourself and set 1-Assigned; tick 01–02; set 3-Resolved. | First Human Response stamped on pick-up; Checklist % 40; Next Action moves to 03; on close: Closed Date today, 03–05 [x], '✅ Resolved on <date> by <you>', close-the-loop email. | Not run
T06 | S1 | Live DATA | Johanna submits and works a real request. | Same as T01–T05 with no manual fixes. | Not run
T07 | S2 | XPAY — HR approval | Submit XPAY (hourly $100, first date worked before this period's cutoff). | 2-Waiting / Pending / Approver; HR approval email; approve → Approved, step 01 [x], 🔓 comment, decision line in Internal Notes; Status 0-New (unassigned) or 1-Assigned. | Not run
T08 | S2 | XPAY — after cutoff | Submit XPAY with first date worked in a period whose cutoff has passed. | Intake comment and Slack show the pay period and ⚠️ after cutoff. | Not run
T09 | S2 | XPAY — rejected | Submit XPAY; reject it. | 3-Resolved; Outcome Rejected; open steps [–]; requester email says it was closed as Rejected; NO Payroll FYI. | Not run
T10 | S2 | XPAY — Payroll FYI | Close the T07 request. | One Payroll room message with the details; editing the closed item again doesn't re-post. | Not run
T11 | S2 | LOA | Submit LOA. | SLA blank ('Per policy'); Assigned To = CJ; Slack shows '(confidential — see list)'; ticking every step doesn't close it. | Not run
T12 | S2 | OFF-V | Submit OFF-V with Effective date = next Friday. | SLA Due Date = that Friday; 16 steps; 'Terminate in Paycor' line shows 📅 date; Priority Time-sensitive. | Not run
T13 | S2 | OFF-I and ER (sensitive) | Submit OFF-I and ER. | Names withheld in Slack; Priority Urgent; ER routed to CJ with summary-only steps. | Not run
T14 | S3 | JOB — two stages | Submit JOB (Manager email = you; Region with a Regional row). | Manager approval first; Regional only after it; both lines in Internal Notes. | Not run
T15 | S3 | COMP — reject at stage 2 | Approve Manager, reject Regional. | HR stage never sent; Rejected path as T09. | Not run
T16 | S3 | No approver | Submit JOB with a Region that has no Regional row and the '*' row set Active = No. | Approval Status = Needs approver; 2-Waiting; Slack alert. Restore the '*' row. | Not run
T17 | S3 | Next Action override | Type your own Next Action, then tick one more step. | Your text stays until the tick, then Next Action moves to the next open step; at 100% '☑️ … ready to resolve'; Status unchanged. | Not run
T18 | S4 | Daily digest | Run Flow 6 with open test items (overdue, 0-New, waiting, an exception). | One Slack post with the right sections; OFF-I / LOA / ER names show '(confidential)'. | Not run
T19 | S4 | Cutoff reminder | Set CutoffDay1 to a date ReminderBusinessDays business days ahead; run Flow 6. | Managers channel reminder with the form link. Restore the setting. | Not run
T20 | S4 | Exception drill | Point Flow 1's Slack step at a channel the service account can't post to; submit DATA. | Admin email with run link; Automation Note; item in Exceptions view and digest. Undo. | Not run
T21 | S0 | Permissions | A non-HR colleague submits the form, then tries the list URL. | Form works; list says they don't have access. | Not run
T22 | S3 | Config without flow edits | Change DATA's SLABusinessDays to 2 in Excel; submit DATA. | SLA = 2 business days. Restore to 1. | Not run

## Decisions
Decisions
Design decisions and the ones that need your confirmation.
ID | Topic | Decision | Why | Status
D1 | System of record | ONE SharePoint list, HR Change Requests, replaces the HR Change Slack List. | Your direction. | Decided
D2 | List shape | The list keeps only the core service-desk columns (from the inspiration) plus the plan's universal fields. Everything request-specific goes in Description and the sub-step Checklist. | One list that stays simple for any HR request. No per-type columns to maintain. | Decided
D3 | Front door | A Microsoft Form (org-only, records the responder) pinned in #lane-people-talent. The list is HR-only; HR can still add items directly for walk-ins or calls. | Requesters never need access to the HR queue (inspiration: don't expose the queue), so Internal Notes stay internal. A Slack form can't write to SharePoint without a bot token. | Confirm (CJ)
D4 | Change types | 16 general HR request types (+ Other) in five groups. Your A1–I types map into them (PlanRef column). | Covers the whole HR team's work, not only HR changes. Add or retire types in Excel. | Confirm (CJ)
D5 | XPAY — Payroll role | Payroll is a verifier, not a gate: a one-way Slack FYI when People Ops closes an XPAY case. | The plan's Flow 3 section says this; the master reference's 'Payroll final approval' line conflicts. To make Payroll a gate, add 'Payroll' to XPAY's ApprovalChain. | Confirm (CJ)
D6 | Reference data | SLAs, approval chains, checklists, approvers, settings and 'info needed' prompts live in one Excel workbook the flows read. | Managed like a reference sheet. Contract: never rename a table or a column header. | Decided
D7 | Checklist / sub-steps | Flow 2 posts the steps to the item's comment thread and writes them to the Checklist field. HR ticks [ ] → [x]; Flow 3 keeps Checklist % and Next Action current. | The plan's Phase 1 thread checklist plus the Phase 2 progress goal, without a second list. | Decided
D8 | Plan Flow 3 (Payroll Notification) | Merged into Flow 4 Close-out: it runs once per closure, and posts the Payroll FYI when the change type says NotifyPayrollOnClose = Yes. | Same behaviour, one less flow, and no extra tracking column. | Decided
D9 | First human response | Stamped automatically the first time a person (not the service account) moves a request off 0-New. | The inspiration's first-response date without manual entry. Needs the flows' SharePoint connection on a service account. | Decided
D10 | Approvals | Power Automate Approvals (email, Teams, app), sequential, from ApprovalChain. Decisions go to the comment thread and Internal Notes. In-Slack buttons wait for the Phase 3 bot token. | Standard connector, no IT app approval. | Decided
D11 | Slack connection | Power Automate Slack connector (OAuth) under a People Ops service account; posts go to channels. | Answers the plan's open question: no bot token needed. | Decided
D12 | Sensitive types | OFF-I, LOA and ER withhold the employee name from Slack and the digest. ER keeps only a summary on the list; details live in the restricted case file. | Limit sensitive content (inspiration: restricted lane). | Decided
D13 | Approval rollout | XPAY's HR approval goes live in Sprint 2 (pilot). JOB, COMP, PTO (and REQ) chains switch on in Sprint 3 by filling ApprovalChain after matrix sign-off. | Matches the plan dependency 'Approval matrix signed off'. | Decided
D14 | SLA calendar | Business days skip weekends, not holidays. | Holiday table is on the Run backlog. | Accepted
D15 | Sensitive data in Description | The form tells people not to type bank numbers, SSNs or medical details. HR collects them securely. | Description is free text and visible to the HR team. | Decided
D16 | Plan typo | 'deparHRent' → 'department' (a find/replace of 'tm' → 'HR'). Check the source doc for other damaged words. |  | FYI

## Inspiration Review
Inspiration Review
What we adopted, adapted, deferred or rejected from the email-ticketing inspiration — and why.
Idea | Verdict | Why | How it shows up
Core ticket columns (reference, requester, category, priority, status, owner, received, first response, next action + due, closed, internal notes) | Adopt | Your direction — a lean, general queue. | They are the list (List Fields tab). Plan fields kept: Employee Name/ID, Manager, Effective Date, SLA Due Date.
Message / conversation identifiers, last inbound date | Defer | Only meaningful with email intake. | Add back if email intake is turned on (the earlier hr-ticketing-triage solution has the matching logic).
Email-first intake | Reject | Breaks 'One front door' and 'Not in the intake, does not exist'. | Adapt: HR mailbox auto-reply points to the form (Sprint 2).
Don't give employees access to the whole HR queue | Adopt | Internal notes and other people's requests must stay private. | Microsoft Forms front door; HR-only list (D3).
One owner + Next action + Next action date on every active case | Adopt | 'In progress' alone doesn't say what happens next. | Flow 3 keeps Next Action = first open sub-step; HR can override.
Richer waiting statuses | Adapt | Keep Tag, You're It 0–3 for continuity. | Waiting On field used with 2-Waiting.
First human response date | Adopt | Shows pick-up speed separately from completion. | Stamped automatically (D9).
Action-based workbench views | Adopt | Fast daily triage. | 8 views, incl. Needs Attention Today and Exceptions.
Daily digest instead of per-update emails | Adopt | Less noise; one place to see risk. | Flow 6, sensitive names withheld.
Restricted lane for sensitive casework | Adapt | Most requests are routine. | ER type with summary-only rule + restricted case file; Sensitive flag hides names.
Ticket Messages list; copying email bodies | Reject | One-list rule; the comment thread is the log.
Send HR responses from list fields | Reject | Complexity for little gain. | Close-the-loop email at resolution; replies in Slack/Outlook.
Auto-close after inactivity | Reject | LOA must stay open; closure is a deliberate HR act. | Digest surfaces stale items.
Exception path — never lose a request | Adopt | A failed step must stay visible. | Try/Catch in every flow → admin email + Automation Note + Exceptions view.
Loop guards | Adopt | Flows that update their own trigger item can loop. | Trigger conditions (Flow 4) and compare-before-write (Flow 3).
Don't promise resolution dates in acknowledgements | Adopt | Sets the right expectation. | Confirmation email says 'target' and lists the info needed.
Pilot scenario list | Adapt | Email-specific cases don't apply. | 22-case Test Pack for HR request paths, approvals, permissions, failures.
Test access with a non-HR account | Adopt | Filtered views are not security. | Test T21.

## Plan Traceability
Plan Traceability
Every element of the project plan and where it is delivered.
Project plan item | Where it lives in the build | Sprint
Guiding principle — One front door | Microsoft Form pinned in #lane-people-talent; HR mailbox auto-reply points to it | S0, S2
Guiding principle — Not in the intake, does not exist | Every case is a list item; views and digest only show list items | S2
Guiding principle — Slack native first | Updated (D3): Microsoft-native for the record, Slack for visibility | S0
Guiding principle — The list is the system of record | ONE SharePoint list with core columns (D1, D2) | S0
Guiding principle — Templates do the thinking | Checklists table → Flow 2 posts the sub-steps | S1
Guiding principle — The thread is the work log | Item comments: intake, checklist, approvals, resolution | S1
Guiding principle — Offboarding is a path | OFF-V / OFF-I are change types on the same list and engine | S2
Layer 1 — Intake + confirmation to submitter | Flow 0 (form → item) + Flow 1 (confirmation email with 'info needed', People Ops ping) | S1
Layer 2 / Phase 1 — Thread-based checklist | Flow 2 checklist comment | S1
Layer 2 / Phase 2 — True subtasks + progress | Checklist field [ ]/[x] + Flow 3 Checklist % and Next Action | S1
Master template items never completed | Checklists table in the reference workbook | S0
Intake fields — universal | Form questions 1–6 + list core columns | S0
Intake fields — conditional by change type | Description + the change type's InfoNeeded prompt (form subtitle, confirmation email, intake comment) | S0, S1
Change types A1–I | Mapped into 16 general HR types (PlanRef column): A1→OFF-V, A2→OFF-I, B→JOB, C→COMP, D→PAY, E→DATA, F→PTO, G→LOA, H→BEN, I→XPAY | S0
List fields — Request ID … Completion date | Ticket Reference, Category, Status, Assigned To, SLA Due Date, Closed Date, Internal Notes (Jira link)… | S0
Status labels 0–3 | Status choice (Statuses tab) | S0
SLA targets by change type | Change Types table → Flow 1 SLA Due Date | S1
Completion auto-comment (✅ Resolved on [date] by [assignee] + stamp date) | Flow 4 Close-out | S1
Flow 1 — Intake Notification | Flow 1 (Flow 0 feeds it from the form) | S1
Flow 2 — Checklist Router (paths + Other catch-all) | Flow 2 (one generic path reads the table; OTHER → 'needs manual scoping') | S1
Flow 3 — Payroll Notification (Template I, not a gate) | Flow 4 Close-out, NotifyPayrollOnClose (D8) | S2
Template I — HR approval → Paycor earning → resolve | XPAY: Flow 5 (HR stage) + checklist + Payroll FYI | S2
Template I — right pay period; flag after cutoff | Flow 1 pay period + after-cutoff flag in the intake comment and Slack | S2
Template G — route to CJ, stays open | LOA default assignee CJ; nothing auto-resolves; Next Action Due = expected return | S2
Approval routing per approval matrix | Flow 5 + Approvers table; switched on after sign-off | S3
Nice to add — cutoff reminder | Flow 6 cutoff reminder | S4
Phase 3 — Dashboard view | Views + daily digest; Power BI later | S4, S6
Phase 3 — Manager self-service form | Already delivered by the Microsoft Form front door; scope can widen | S2
Phase 3 — Bot token / in-Slack approvals; Paycor iPaaS | Run backlog | S6
Build order — E first, then I, then G | DATA end to end (S1), then XPAY pilot, then LOA (S2) | S1, S2
Open question — Slack app vs Power Automate connector | Answered: connector (D11) | S0

## Dependencies
Dependencies
From the plan's dependencies table, plus what this build adds.
Item | Owner | Status | Needed by | Notes
HR Change Reference.xlsx stored on the People Ops site | CJ | Ready (this kit) | S0 | Flows read it.
People Ops service account (SharePoint + Slack connections) | CJ / IT | To confirm | S0 | Needed for the first-response stamp and for Slack posts.
Change types and form wording signed off | CJ / Johanna | To confirm | S0 | Gate 0.
Approval matrix signed off by stakeholders | CJ | To confirm | S3 | Switches on JOB, COMP, PTO, REQ approvals.
Jira connector access + HR Jira project | IT | To confirm | S5 | Plan open question.
Shared offboarding email distro exists and is current | CJ / Johanna | To confirm | S5 | Plan open question.
Word termination letter template | CJ | To build | S5 | 'Populate a Microsoft Word template' is a premium action.
Monday backfill request form URL | Talent | To confirm | S5
Payroll Monday board — column/item | Sydney / Sandra | To confirm | S5 | Plan open question.
Paycor bot token / iPaaS | IT / Paycor CSM | Pending | S6 | Run phase.

## Comms
Launch comms (Sprint 2)
Replace <IntakeFormUrl> with the real link.
Where | Text
#lane-people-talent announcement (pin it) | 📣 *New: one front door for HR requests* From today, every HR request — onboarding, job or pay changes, time off, leave, benefits, letters, questions, offboarding, extra shifts — goes through this form: <FormUrl> • You'll get a confirmation with a ticket reference, a target date and what we need from you. • If it needs approval, the approver gets it automatically. • You'll hear back when it's done. Requests sent by DM or email will be pointed back here — if it isn't in the intake, we can't track it. Thank you! — People Ops
HR mailbox automatic reply | Thanks for reaching out to People Ops. HR requests are handled through our request form so nothing gets lost: <FormUrl>. For anything else, a member of the team will reply soon.